## Sprint 5 Overview
Type	Item	Link	Estimation	Development Hours	QA Hours	PM Hours
Bug	TD-387--IOS: Notification delay	https://tussly.atlassian.net/browse/TD-387	1.5	1.5
Bug	TD-282 -- Edit Chat message is not working properly	https://tussly.atlassian.net/browse/TD-282	4.45	4.42
Bug	TD-339-- IOS : Received notification in the group chat	https://tussly.atlassian.net/browse/TD-339	0.5	0.5
Bug	TD-386--Notification click redirection	https://tussly.atlassian.net/browse/TD-386	1.5	1.75
Bug	TD-349--User shows as online even when user is closed or logout	https://tussly.atlassian.net/browse/TD-349	1.2	1.17
Bug	TD-280 -- User shows as online even when app is closed or in background	https://tussly.atlassian.net/browse/TD-280	0.5	0.5
Bug	TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	https://tussly.atlassian.net/browse/TD-278	3.33	3.33
Bug	TD-281 -- Showing Typing Indicator even when app is closed	https://tussly.atlassian.net/browse/TD-281	0.67	0.67
Bug	TD-272 -- IOS app crashes when clicking on chat	https://tussly.atlassian.net/browse/TD-272	2.17	2.17
Bug	TD-275 -- Chat page should be refreshed.	https://tussly.atlassian.net/browse/TD-275	0.92	0.92
Bug	TD-340 -- IOS : Group chat scrolling is not working	https://tussly.atlassian.net/browse/TD-340	3.67	3.67
Bug	TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message	https://tussly.atlassian.net/browse/TD-290	2.5	2.5
Bug	TD-276 -- Chat Listing page should be refreshed.	https://tussly.atlassian.net/browse/TD-276	1	1
Bug	TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.	https://tussly.atlassian.net/browse/TD-270	0.33	0.33
Bug	TD-286 -- Unable to Delete Message from Reply Thread	https://tussly.atlassian.net/browse/TD-286	0.95	0.95
Bug	TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-291	1.5	1.5
Bug	TD-342--Show the loader when attachment is sent	https://tussly.atlassian.net/browse/TD-342	0.5	0.5
Story	TD-347 -- iOS - Display Action Message in Chat	https://tussly.atlassian.net/browse/TD-347	3	3.33
Bug	TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	https://tussly.atlassian.net/browse/TD-353	1.12	1.12
Bug	TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-293	1.75	1.92
Bug	TD-283 -- Showing Typing Indicator even when app is closed	https://tussly.atlassian.net/browse/TD-283	3.33	3.33
Bug	TD-277 -- Chat Listing page should be refreshed.	https://tussly.atlassian.net/browse/TD-277	0.75	0.75
Bug	TD-285-- Loader moves continuously not stop	https://tussly.atlassian.net/browse/TD-285	1.75	1.75
Story	TD-346--Display Action Message in Chat	https://tussly.atlassian.net/browse/TD-346	3	3.33
Bug	TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel	https://tussly.atlassian.net/browse/TD-341	0.95	0.95
Bug	TD-343--Android: Show the loader when attachment is sent	https://tussly.atlassian.net/browse/TD-343	0.17	0.17
Bug	TD-284 -- Application is crashed when delete the message.	https://tussly.atlassian.net/browse/TD-284	0.17	0.34
Story	TD-240 -- iOS - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-240	7.5	9.17
Story	TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-238	4.5	4.92
Story	TD-234 -- iOS - Step #9-1 -- Send Notification	https://tussly.atlassian.net/browse/TD-234	3	3.33
Story	TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-232	12	12.58
Story	TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat	https://tussly.atlassian.net/browse/TD-231	3	3.25
Story	TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members	https://tussly.atlassian.net/browse/TD-230	3.5	3.75
Story	TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-224	2.5	2.75
Story	TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-260	4.5	4.75
Story	TD-256 -- AND - Step #9-1 -- Send Notification	https://tussly.atlassian.net/browse/TD-256	3	3.25
Story	TD-262 -- AND - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-262	7.5	9.25
Story	TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-254	12	12.75
Story	TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat	https://tussly.atlassian.net/browse/TD-253	3	3.5
Bug	TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-292	2.2	2.17
Bug	TD-289-- Remove the Tost message	https://tussly.atlassian.net/browse/TD-289	0.67	0.67
Bug	TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat	https://tussly.atlassian.net/browse/TD-279	2.5	4.25
Bug	TD-369--Message Input Loses Focus After Sending in Chat	https://tussly.atlassian.net/browse/TD-369	1.25	1.25
Bug	TD-362--Three-Dot Menu Overlaps with Message Layout	https://tussly.atlassian.net/browse/TD-362	2.17	2.17
Bug	TD-273 -- Show the login and close button instead of ok	https://tussly.atlassian.net/browse/TD-273	1.1	1.08
Bug	TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	https://tussly.atlassian.net/browse/TD-373	2.17	2.17
Bug	TD-354--Thread Replies Still Visible After Main Message Is Deleted	https://tussly.atlassian.net/browse/TD-354	0.7	0.7
Bug	TD-360--New Message Not Sending After Editing a Previous Message	https://tussly.atlassian.net/browse/TD-360	1.25	1.25
Story	TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	https://tussly.atlassian.net/browse/TD-359	2.25	2.25
Bug	TD-357--Add the attachment functionality inside the thread.	https://tussly.atlassian.net/browse/TD-357	4.25	4.25
Bug	TD-356--Edit Option Should Not Appear for Image and Document	https://tussly.atlassian.net/browse/TD-356	0.67	0.67
Bug	TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	https://tussly.atlassian.net/browse/TD-355	2.25	2.25
Bug	TD-352--Three-dot message menu does not close on outside click	https://tussly.atlassian.net/browse/TD-352	1.17	1.17
Bug	TD-351--Increase Clickable Area for Document Download in Chat	https://tussly.atlassian.net/browse/TD-351	0.67	0.67
Bug	TD-350--Set the Proper design	https://tussly.atlassian.net/browse/TD-350	0.67	0.67
Bug	TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-348	2.17	2.17
Story	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	https://tussly.atlassian.net/browse/TD-269	16	14.5
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	14	13.75
Story	TD-217 -- Web - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-217	2	4.58
Story	TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result	https://tussly.atlassian.net/browse/TD-214	1	1.25
Story	TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)	https://tussly.atlassian.net/browse/TD-213	1	1.33
Story	TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group	https://tussly.atlassian.net/browse/TD-212	2	1.75
Story	TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens	https://tussly.atlassian.net/browse/TD-211	2	3.25
Story	TD-210 -- Web - Step #5-3 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-210	2	2.33
Story	TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-207	2	2.5
Story	TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-206	3	1.17
Story	TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-205	3	3.25
Story	TD-186 -- Web - Step #4-2 -- Logout from CometChat	https://tussly.atlassian.net/browse/TD-186	2	2
Story	TD-185 -- Web - Step #4-1 -- Login to CometChat	https://tussly.atlassian.net/browse/TD-185	3	1.92
Story	TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members	https://tussly.atlassian.net/browse/TD-252	3.5	3.8
Story	TD-261 -- AND - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-261	7	7.5
Story	TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-246	2.5	2.47
Story	TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat	https://tussly.atlassian.net/browse/TD-235	3.33	3.33
Story	TD-257 -- AND - Step #9-2 -- Do Not Send Notifications for Group Chat	https://tussly.atlassian.net/browse/TD-257	0.25	0.25
Story	TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-251	3	6.05
Story	TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-229	3	3.25
Story	TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-223	2.5	2.58
Bug	TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-294	0.75	0.92
Story	TD-182 -- BE - Step #10 -- Notification Setup	https://tussly.atlassian.net/browse/TD-182	8	3.5
Story	TD-179 -- BE - Step #7 -- API to Identify Whether a User is a Friend or Not	https://tussly.atlassian.net/browse/TD-179	4	3.5
Story	TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-245	2.5	2.92
Story	TD-258 -- AND - Customization #2-1 -- Display Unread Message Count	https://tussly.atlassian.net/browse/TD-258	2	3.08
Story	TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count	https://tussly.atlassian.net/browse/TD-236	2	2.16
Bug	TD-271 -- Display the same consistent message on iOS as shown on Android.	https://tussly.atlassian.net/browse/TD-271	0	0.42
Story	TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App	https://tussly.atlassian.net/browse/TD-244	2	2.3
Story	TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App	https://tussly.atlassian.net/browse/TD-222	2	2.33
Story	TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App	https://tussly.atlassian.net/browse/TD-243	2	2.15
Story	TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App	https://tussly.atlassian.net/browse/TD-221	2	2.08
Story	TD-250 -- AND - Step #5-4 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-250	2	3
Story	TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-228	2	3
Story	TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-249	2.5	3.85
Story	TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-227	2.5	4.17
Story	TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-247	2.5	3.2
Story	TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-225	2.5	2.75
Story	TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-248	5.33	5.92
Story	TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-226	5.33	5.75
Story	TD-181 -- BE - Step #9 -- Manage Flag for Disabling Chat	https://tussly.atlassian.net/browse/TD-181	3	3
Story	TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat	https://tussly.atlassian.net/browse/TD-180	4	4
Story	TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players	https://tussly.atlassian.net/browse/TD-178	12	8.5
Story	TD-177 -- BE - Step #5 -- Register User in CometChat Upon Signup	https://tussly.atlassian.net/browse/TD-177	3	3
Story	TD-268 -- BE - Step #4A -- Sync All the old teams	https://tussly.atlassian.net/browse/TD-268	5	5
Story	TD-184 -- Web - Step #3-2 -- Initialize CometChat SDK	https://tussly.atlassian.net/browse/TD-184	2	2
Story	TD-183 -- Web - Step #3-1 -- Integrate CometChat SDK	https://tussly.atlassian.net/browse/TD-183	3	2
Story	TD-176 -- BE - Step #4 -- Sync All Old App Users	https://tussly.atlassian.net/browse/TD-176	7	5.5
Story	TD-175 -- BE - Step #3 -- Integrate CometChat SDK	https://tussly.atlassian.net/browse/TD-175	2	1.5
Story	TD-242 -- AND - Step #3-2 -- Initialize CometChat SDK	https://tussly.atlassian.net/browse/TD-242	2	2
Story	TD-220 -- iOS - Step #3-2 -- Initialize CometChat SDK	https://tussly.atlassian.net/browse/TD-220	2	2
Story	TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)	https://tussly.atlassian.net/browse/TD-174	4	2.5
Story	TD-219 -- iOS - Step #3-1 -- Integrate CometChat SDK	https://tussly.atlassian.net/browse/TD-219	3	2.83
Story	TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page	https://tussly.atlassian.net/browse/TD-216	1	1.25
Story	TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	https://tussly.atlassian.net/browse/TD-215	1	4.5
Story	TD-239 -- iOS - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-239	7	8
Story	TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality	https://tussly.atlassian.net/browse/TD-255	4	4.3
Story	TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality	https://tussly.atlassian.net/browse/TD-233	4	4.5
Story	TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-207	2	2.5
Bug	TD-385--Notification click redirection	https://tussly.atlassian.net/browse/TD-385	0.25	0.25
Task	TD-405 -- Web - Enable or Implement “Invite via Link” Functionality on Team Page	https://tussly.atlassian.net/browse/TD-405	1	1
Bug	TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	https://tussly.atlassian.net/browse/TD-408	8.5	8.5
Bug	TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	https://tussly.atlassian.net/browse/TD-409	8	8
Bug	TD-428 -- AND - App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	https://tussly.atlassian.net/browse/TD-428	5	5
Bug	TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	https://tussly.atlassian.net/browse/TD-421	2.25	2.25
Bug	TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	https://tussly.atlassian.net/browse/TD-415	2.33	2.33
Task	TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	https://tussly.atlassian.net/browse/TD-418	1.25	1.25
Bug	TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	https://tussly.atlassian.net/browse/TD-424	1.17	1.17
Bug	TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-416	4.25	4.25
Bug	TD-411 -- iOS - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	https://tussly.atlassian.net/browse/TD-411	3	3
Bug	TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	https://tussly.atlassian.net/browse/TD-427	1.17	1.17
Bug	TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-423	1.42	1.42
Bug	TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	https://tussly.atlassian.net/browse/TD-426	1	1
Bug	TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	https://tussly.atlassian.net/browse/TD-425	2.17	2.17
Bug	TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	https://tussly.atlassian.net/browse/TD-414	0.42	0.42
Bug	TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	https://tussly.atlassian.net/browse/TD-412	0.34	0.34
Bug	TD-420 -- iOS Users Do Not Receive First Message from Organizer in Arena Chat	https://tussly.atlassian.net/browse/TD-420	2	2
Bug	TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	https://tussly.atlassian.net/browse/TD-419	3.33	3.33
Bug	TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	https://tussly.atlassian.net/browse/TD-417	3.17	3.17
Bug	TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	https://tussly.atlassian.net/browse/TD-413	2.5	2.5
Story	TD-410 -- Dismiss Keyboard on Outside Tap	https://tussly.atlassian.net/browse/TD-410	3	3
			395.8	413.64	41.95	19.11

## Sprint 5 Log
Type	Item	Link	Notes	Hours	Person	Date
	Call With CometChat		Call With CometChat	1	Jayesh Rathod	2025-07-03
	Call With CometChat		Call With CometChat	1	Pranay Prajapati	2025-07-03
Bug	TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	https://tussly.atlassian.net/browse/TD-417	Verified Arena chat functions continuously without any interruptions during a match. Confirmed no crashes occur during regular Arena chat usage.	0.5	Kinjal Shah	2025-07-02
Story	TD-410 -- Dismiss Keyboard on Outside Tap	https://tussly.atlassian.net/browse/TD-410	Check all possible page contain input in TextField and/or TextView. Dismiss keyboard on out side tap.	3	Pranay Prajapati	2025-07-01
Bug	TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	https://tussly.atlassian.net/browse/TD-415	Tested that clicking on the chat icon successfully creates a group chat with the organizer and the players/teams. Tested that the organizer is routed to the newly created chat, or sees a confirmation that the chat has been created. Tested that if the chat already exists, clicking the icon should route the organizer to the existing chat instead of trying to create a duplicate.	0.33	Kinjal Shah	2025-07-01
Task	TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	https://tussly.atlassian.net/browse/TD-418	Tested that set the Return to Previous Section button is visible to organizers on the Chat page. Confirmed that clicking the button returns the organizer to the last visited page before entering Chat. Ensured that the navigation flow is consistent regardless of the entry point into Chat, including:Tournament Dashboard, Team, or Player Detail pages and other pages.	0.25	Kinjal Shah	2025-07-01
Bug	TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	https://tussly.atlassian.net/browse/TD-421	Tested that clicking “Leave Group” successfully removes the Organizer from the chat group. Confirmed that the chat is no longer visible in the Organizer’s main chat after leaving. Validated that no chat data, access, occurs after exit.	0.25	Kinjal Shah	2025-07-01
Bug	TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	https://tussly.atlassian.net/browse/TD-419	Tested that iOS users can successfully tap "Call Organizer," and an organizer is added to the chat. Ensured that the organizer joins the chat without requiring the user to restart the app. Tested that the feature works consistently across both iOS and Android platforms. The user sees the organizer added without needing to navigate away or refresh the screen.	0.33	Kinjal Shah	2025-07-01
Bug	TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	https://tussly.atlassian.net/browse/TD-424	Tested that a confirmation pop-up appears when the “Add Admin” button is clicked. Confirmed that selecting "Yes" adds an admin and updates the chat accordingly. Confirmed that selecting "Cancel" closes the pop-up without taking any action. Ensured the confirmation modal follows standard UI styling and appears consistent with other system dialogs. Verify that no duplicate admins are added.	0.17	Kinjal Shah	2025-07-01
Bug	TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-416	Verified that when a new message is received in an Arena chat, the corresponding Arena red badge icon displays a message indicator. Confirmed that the red dot indicator disappears immediately once the user opens the Arena chat. Checked that entering the Arena chat marks messages as read and removes the red dot indicator without delay. Validated that the main Chat icon behavior remains unchanged — no interference or unexpected updates triggered by Arena chat unread status.	0.25	Kinjal Shah	2025-07-01
Bug	TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	https://tussly.atlassian.net/browse/TD-413	Tested that upon returning from the background, the app immediately fetches and displays the correct number of unread conversations on the main chat icon. Tested that the badge count updates without needing to navigate to the chat page. Ensured that real-time badge updates continue to work properly while the app remains open. Validated that no delay or manual action is required to refresh the unread badge count after resuming the app.	0.25	Kinjal Shah	2025-07-01
Bug	TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	https://tussly.atlassian.net/browse/TD-425	Tested the same scenario, but it was not found as discussed with the developer. They have set the scenario below. When chat history and real-time events do not load on initial login, ensure proper synchronization without requiring a manual logout and login.	0.17	Kinjal Shah	2025-07-01
Bug	TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-423	Retest the chat count issue after reading the arena chat.	0.17	Kinjal Shah	2025-07-01
Bug	TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	https://tussly.atlassian.net/browse/TD-413	While user put application in the background, then send messages from other user and then again active the application from the background. This time we identify the application become active then again get unread message count and update the badge.	2.25	Pranay Prajapati	2025-06-28
Bug	TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	https://tussly.atlassian.net/browse/TD-412	Tested that when a message is deleted before the recipient reads it, no second push notification is sent. Ensured that the deletion of messages already seen triggers no push notifications.	0.17	Kinjal Shah	2025-06-28
Bug	TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	https://tussly.atlassian.net/browse/TD-414	Tested that no additional push notification is sent to the recipient when a message is edited. Tested that the edited message updates correctly and is reflected in the chat view for the recipient. Validated that the edited message appears correctly, whether it was: Already read by the recipient Performed cross-platform testing on iOS and Android	0.25	Kinjal Shah	2025-06-28
Bug	TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	https://tussly.atlassian.net/browse/TD-427	Tested that a confirmation pop-up appears when the “Add Admin” button is clicked. Confirmed that selecting "Yes" adds an admin and updates the chat accordingly. Confirmed that selecting "Cancel" closes the pop-up without taking any action. Ensured the confirmation modal follows standard UI styling and appears consistent with other system dialogs. Verify that no duplicate admins are added.	0.17	Kinjal Shah	2025-06-28
Bug	TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-423	Verified that when a new message is received in an Arena chat, the corresponding Arena red dot icon displays a message indicator. Confirmed that the red dot indicator disappears immediately once the user opens the Arena chat. Checked that entering the Arena chat marks messages as read and removes the red dot indicator without delay. Validated that the main Chat icon behavior remains unchanged — no interference or unexpected updates triggered by Arena chat unread status.	0.25	Kinjal Shah	2025-06-28
Bug	TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	https://tussly.atlassian.net/browse/TD-426	Tested that upon returning from the background, the app immediately fetches and displays the correct number of unread conversations on the main chat icon. Tested that the badge count updates without needing to navigate to the chat page. Ensured that real-time badge updates continue to work properly while the app remains open. Validated that no delay or manual action is required to refresh the unread badge count after resuming the app.	0.25	Kinjal Shah	2025-06-28
Bug	TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	https://tussly.atlassian.net/browse/TD-417	Checking this issue and try to identify and reproduce this issue.	2.67	Pranay Prajapati	2025-06-27
Bug	TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	https://tussly.atlassian.net/browse/TD-419	Check all scenario and try to find this issue, and we get this issue, while user create group and that time we user on behalf. So one user stays member that's why this issue happen. For this make both user admin.	3	Pranay Prajapati	2025-06-27
Bug	TD-420 -- iOS Users Do Not Receive First Message from Organizer in Arena Chat	https://tussly.atlassian.net/browse/TD-420	We are try to identify and reproduce this issue, but not able to find. We raised this issue in CometChat.	2	Pranay Prajapati	2025-06-27
Bug	TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	https://tussly.atlassian.net/browse/TD-412	Disable Notification for edit notification.	0.17	Pranay Prajapati	2025-06-27
Bug	TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	https://tussly.atlassian.net/browse/TD-414	Disable Notification for edit notification.	0.17	Pranay Prajapati	2025-06-27
Bug	TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	https://tussly.atlassian.net/browse/TD-425	Fix issue where chat history and real-time events do not load on initial login, ensuring proper synchronization without requiring a manual logout and login.	2	HasanAli	2025-06-27
Bug	TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	https://tussly.atlassian.net/browse/TD-426	Ensure the main chat icon updates with the correct unread message count when the app resumes from the background after receiving messages.Ensure the main chat icon updates with the correct unread message count when the app resumes from the background after receiving messages.	0.75	HasanAli	2025-06-27
Bug	TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-423	Fix the missing unread message counter on the Arena chat icon to display the indicator in real-time.	1	HasanAli	2025-06-27
Bug	TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	https://tussly.atlassian.net/browse/TD-427	Add a confirmation pop-up to verify the user's intent before assigning admin rights to a member in the Arena chat.	1	HasanAli	2025-06-27
Bug	TD-411 -- iOS - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	https://tussly.atlassian.net/browse/TD-411	Here we try to identify and reproduce issue, and one time we get this issue while auth token expire but user is login. So solve this issue, while user go to chat list screen and call for get conversation list. This time we identify the auth token issue and then logout and again login cometchat user. Then again call get conversation.	3	Pranay Prajapati	2025-06-26
Bug	TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	https://tussly.atlassian.net/browse/TD-416	Update all arena screen design for display unread chat message indicator.	4	Pranay Prajapati	2025-06-26
Bug	TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	https://tussly.atlassian.net/browse/TD-424	Add a confirmation pop-up to Add Admin.	1	Pranay Prajapati	2025-06-26
Task	TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	https://tussly.atlassian.net/browse/TD-418	Added back functionality with the word “Return to Previous Section“	1	Usama Shaikh	2025-06-26
Bug	TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	https://tussly.atlassian.net/browse/TD-415	Added Join group functionality when join group from scoreboard & results ans schedule bracket	2	Usama Shaikh	2025-06-26
Bug	TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	https://tussly.atlassian.net/browse/TD-421	Added Leave group functionality when leave group click in group chat	2	Usama Shaikh	2025-06-26
Bug	TD-428 -- AND - App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	https://tussly.atlassian.net/browse/TD-428	It was observed that when both users are on the chat message screen, the first message sent by one user is received by the other but is not displayed in the message list. This was due to missing or incorrect update conditions when handling the first message. To resolve this, the logic was updated to properly fetch the first message and refresh the conversation and user details accordingly—for both text and media messages—ensuring the message list updates correctly in real time.	5	HasanAli	2025-06-20
Bug	TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	https://tussly.atlassian.net/browse/TD-409	While the app did not crash, it was observed that when both users are on the chat message screen, the first message sent by one user is received by the other but is not displayed in the message table. This was due to missing or incorrect update conditions when handling the first message. To resolve this, the logic was updated to properly fetch the first message and refresh the conversation and user details accordingly—for both text and media messages—ensuring the message list updates correctly in real time.	5	Pranay Prajapati	2025-06-20
Bug	TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	https://tussly.atlassian.net/browse/TD-408	Uploaded the latest dSYM file to Firebase Crashlytics to ensure accurate crash reporting and symbolication. This allows better visibility into stack traces and helps with debugging crash issues more effectively. To address potential causes, updated all project dependencies (including CometChat) and carefully reviewed Info.plist entries to ensure all required permissions are correctly declared. These changes were made to prevent any unintended use of audio-related APIs by third-party SDKs and to eliminate possible privacy violations. The goal is to improve overall app stability and ensure compliance with iOS privacy expectations.	4	Pranay Prajapati	2025-06-20
Bug	TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	https://tussly.atlassian.net/browse/TD-409	Tested the reported crash scenario on iOS by installing the app via TestFlight, registering new users, entering the chatroom, and triggering both typing indicators and sending the first message from a newly added friend. Repeated the steps multiple times to simulate the exact conditions under which the crash occurs. However, the issue could not be reproduced on iOS—no crash was observed, and the app remained stable throughout.	3	Pranay Prajapati	2025-06-19
Bug	TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	https://tussly.atlassian.net/browse/TD-408	Thoroughly tested the app in various scenarios, including fresh installs, new user registrations, and prolonged idle states after launch. Although the issue was reported to occur 30–45 seconds after launch (especially for new users), it could not be reproduced during testing via TestFlight. The app remained stable, and the crash did not occur. However, an orange microphone indicator was consistently visible in the multitasking view, despite no microphone permissions being requested or visible in iOS settings.	4.5	Pranay Prajapati	2025-06-19
Task	TD-405 -- Web - Enable or Implement “Invite via Link” Functionality on Team Page	https://tussly.atlassian.net/browse/TD-405	Get the data from the embedded link, Convert into JSON & set to the local object. Data saved in local Storage	1	Usama Shaikh	2025-06-18
Bug	TD-386--Notification click redirection	https://tussly.atlassian.net/browse/TD-386	Test the notification redirection.	0.25	Kinjal Shah	2025-06-12
Bug	TD-385--Notification click redirection	https://tussly.atlassian.net/browse/TD-385	Test the notification redirection.	0.25	Kinjal Shah	2025-06-12
Bug	TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-294	Retest the bug	0.17	Kinjal Shah	2025-06-11
Bug	TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-293	Retest the bug	0.17	Kinjal Shah	2025-06-11
Bug	TD-284 -- Application is crashed when delete the message.	https://tussly.atlassian.net/browse/TD-284	Retest the bug	0.17	Kinjal Shah	2025-06-10
Bug	Call With CometChat		Call With CometChat	1	Jayesh Rathod	2025-06-12
Bug	Call With CometChat		Call With CometChat	1	Pranay Prajapati	2025-06-12
Bug	TD-387--IOS: Notification delay	https://tussly.atlassian.net/browse/TD-387	I have place this issue in ComeChat support. We are working on it.	1.5	Pranay Prajapati	2025-06-10
Bug	TD-282 -- Edit Chat message is not working properly	https://tussly.atlassian.net/browse/TD-282	Retest the bug	0.17	Kinjal Shah	2025-06-10
Bug	TD-339-- IOS : Received notification in the group chat	https://tussly.atlassian.net/browse/TD-339	Change notification register method in CometChat, after this notification payload change, need to access new payload update code.	0.33	Pranay Prajapati	2025-06-09
Bug	TD-386--Notification click redirection	https://tussly.atlassian.net/browse/TD-386	After method change of notification register for cometchat then after payload change based on new notification system. So update my navigation code.	1.5	Pranay Prajapati	2025-06-09
Bug	TD-349--User shows as online even when user is closed or logout	https://tussly.atlassian.net/browse/TD-349	Retest the bug	0.17	Kinjal Shah	2025-06-09
Bug	TD-280 -- User shows as online even when app is closed or in background	https://tussly.atlassian.net/browse/TD-280	Retest the bug	0.33	Kinjal Shah	2025-06-09
Bug	TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	https://tussly.atlassian.net/browse/TD-278	Retest the bug	0.33	Kinjal Shah	2025-06-09
Bug	TD-281 -- Showing Typing Indicator even when app is closed	https://tussly.atlassian.net/browse/TD-281	Retest the bug	0.17	Kinjal Shah	2025-06-09
Bug	TD-282 -- Edit Chat message is not working properly	https://tussly.atlassian.net/browse/TD-282	Retest the bug	0.25	Kinjal Shah	2025-06-09
Bug	TD-272 -- IOS app crashes when clicking on chat	https://tussly.atlassian.net/browse/TD-272	Retest the bug	0.17	Kinjal Shah	2025-06-09
Bug	TD-275 -- Chat page should be refreshed.	https://tussly.atlassian.net/browse/TD-275	Retest the bug	0.17	Kinjal Shah	2025-06-09
Bug	TD-340 -- IOS : Group chat scrolling is not working	https://tussly.atlassian.net/browse/TD-340	Retest the bug	0.17	Kinjal Shah	2025-06-09
Bug	TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message	https://tussly.atlassian.net/browse/TD-290	Retest the bug	0.25	Kinjal Shah	2025-06-09
Bug	TD-349--User shows as online even when user is closed or logout	https://tussly.atlassian.net/browse/TD-349	Checked & set ht eproper logic whne user online & offlie	1	Usama Shaikh	2025-06-06
Bug	TD-339-- IOS : Received notification in the group chat	https://tussly.atlassian.net/browse/TD-339	Retest the bug	0.17	Kinjal Shah	2025-06-06
Bug	TD-276 -- Chat Listing page should be refreshed.	https://tussly.atlassian.net/browse/TD-276	Retest the bug	0.17	Kinjal Shah	2025-06-06
Bug	TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.	https://tussly.atlassian.net/browse/TD-270	Retest the bug	0.08	Kinjal Shah	2025-06-06
Bug	TD-286 -- Unable to Delete Message from Reply Thread	https://tussly.atlassian.net/browse/TD-286	Retest the bug	0.2	Kinjal Shah	2025-06-06
Bug	TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-291	Retest the bug	0.17	Kinjal Shah	2025-06-06
Bug	TD-342--Show the loader when attachment is sent	https://tussly.atlassian.net/browse/TD-342	Retest the bug. from thread also.	0.17	Kinjal Shah	2025-06-06
Story	TD-347 -- iOS - Display Action Message in Chat	https://tussly.atlassian.net/browse/TD-347	Verified that an action message is displayed when a user is added as an admin. Tested that the action message is styled differently from user messages. Checked real-time visibility of the action message for all logged-in users. Ensured that the message is visible in chat history. Ensured no duplicate or repeated action messages are shown. Checked that the action message does not interfere with normal chat messages.	0.33	Kinjal Shah	2025-06-06
Bug	TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	https://tussly.atlassian.net/browse/TD-353	Retest the bug	0.12	Kinjal Shah	2025-06-06
Bug	TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-293	Retest the bug	0.25	Kinjal Shah	2025-06-06
Bug	TD-283 -- Showing Typing Indicator even when app is closed	https://tussly.atlassian.net/browse/TD-283	This issue has been resolved. When use kill the app, then typing indicator will not show for other user .	0.33	Kinjal Shah	2025-06-06
Bug	TD-277 -- Chat Listing page should be refreshed.	https://tussly.atlassian.net/browse/TD-277	Retest the bug	0.25	Kinjal Shah	2025-06-06
Bug	TD-285-- Loader moves continuously not stop	https://tussly.atlassian.net/browse/TD-285	Retest the bug	0.25	Kinjal Shah	2025-06-06
Story	TD-346--Display Action Message in Chat	https://tussly.atlassian.net/browse/TD-346	Verified that an action message is displayed when a user is added as an admin. Tested that the action message is styled differently from user messages. Checked real-time visibility of the action message for all logged-in users. Ensured that the message is visible in chat history. Ensured no duplicate or repeated action messages are shown. Checked that the action message does not interfere with normal chat messages.	0.33	Kinjal Shah	2025-06-06
Bug	TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel	https://tussly.atlassian.net/browse/TD-341	Retest the bug from main chat and thread chat	0.2	Kinjal Shah	2025-06-06
Bug	TD-343--Android: Show the loader when attachment is sent	https://tussly.atlassian.net/browse/TD-343	Retest the bug	0.17	Kinjal Shah	2025-06-06
Bug	TD-284 -- Application is crashed when delete the message.	https://tussly.atlassian.net/browse/TD-284	Not able to reproduce this issue.	0.17	Pranay Prajapati	2025-06-05
Bug	TD-280 -- User shows as online even when app is closed or in background	https://tussly.atlassian.net/browse/TD-280	Issue assign to CometChat, but still not get an proper solution. And also issue not reproduce again.	0.17	Pranay Prajapati	2025-06-05
Story	TD-240 -- iOS - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-240	Verified long press on a message shows the Reply option. Confirmed tapping Reply opens a dedicated thread view screen. Tested that parent message is displayed at the top of the thread screen. Verified that replies are listed correctly below the parent message. Verified that replies are visible to all participants in real-time. Tested that the thread updates instantly on new incoming replies. Tested that real-time edit and delete changes in the thread. Verified user can edit their reply from the thread view. Confirmed edited replies update in real-time for all users. Verified user can delete their reply and it is removed from all views. Tested back navigation returns to main chat. Tested thread design separates parent and child messages clearly. Validated threaded replies persist across refresh and logout/login. Tested thread reply count shows accurately. Tested tapping reply count in main chat navigates to the correct thread.	1.17	Kinjal Shah	2025-06-04
Story	TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-238	Tested that Chat input field is disabled after match completion. Verified that Previously sent messages are still visible in read-only mode. A "Match Finished" label is displayed clearly in the chat UI. Tested that "Chat is disabled. Match has ended." Tested that Users are not able to re-enable chat after the match ends. Verified that Match completion behavior applies only to arena-type group chats. Verified Other group chats are unaffected by this logic.	0.42	Kinjal Shah	2025-06-04
Story	TD-234 -- iOS - Step #9-1 -- Send Notification	https://tussly.atlassian.net/browse/TD-234	Verified that when a message is sent, a notification is triggered for the recipient. Tested that no notification is sent if the recipient is logged out. When the recipient’s app is in the foreground, confirm that an in-app notification is displayed. When the app is in the background, verify that a push notification appears in the app. Tested on both Android and iOS for system notification behavior. Verified notification content shows sender name and message preview correctly. Confirmed badge count are displayed properly on the app icon. Tested that the app does not crash during notification delivery failures. Confirmed that read status syncs after notification tap and chat screen opens.	0.58	Kinjal Shah	2025-06-04
Story	TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-232	Verified that Chat Icon is visible in Arena and clickable for all logged-in users. Confirmed user is navigated to Chat Message Screen if chat already exists. Verified "Contact Admin" button is visible on Chat Message Screen. Tested that if the admin is not added, clicking on ‘Contact Admin’ will add the admin. Tested that if the admin is already added, it will show the message that the admin has already been added. Ensured admin chat is persistent across refresh/log out-log in scenarios. Ensured UI responsiveness and smooth screen transitions. Tested that no duplicate chats are created. Tested that chat history loads correctly.	0.58	Kinjal Shah	2025-06-04
Story	TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat	https://tussly.atlassian.net/browse/TD-231	Verified that tapping the "Contact Admin" tab triggers a check for an existing chat conversation. And verified that if the chat exists, the user is navigated to the Chat Message Screen without delay. Verified that if the chat does not exist, the system initiates an API call to create a new chat with the admin. Tested that If the user is not logged in, confirmed that the system redirects them to the Login screen instead of initiating the chat flow. Ensured the chat screen loads recent messages smoothly once opened.	0.5	Kinjal Shah	2025-06-04
Story	TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members	https://tussly.atlassian.net/browse/TD-230	Tested that only team members are able to send and receive messages within the team chat. Tested the "Chat" tab on the Team Player Card. Confirmed non-team members are not allowed to chat. Validated logout scenarios to ensure redirection to the Login Screen when a logged-out user taps the chat tab. Ensured the team chat screen loads recent messages smoothly upon access. Tested the team chat functionality, sending multiple msg with media file and all.	0.5	Kinjal Shah	2025-06-04
Story	TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-224	Verified that logging out from the app successfully triggers the CometChat logout request. Confirmed that the logout was successful with no errors encountered during testing. No retry was required, as CometChat logout completed successfully on the first attempt. No error message was displayed, indicating that the logout process worked as intended.	0.25	Kinjal Shah	2025-06-04
Story	TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-260	Tested that Chat input field is disabled after match completion. Verified that Previously sent messages are still visible in read-only mode. A "Match Finished" label is displayed clearly in the chat UI. Tested that "Chat is disabled. Match has ended." Tested that Users are not able to re-enable chat after the match ends. Verified that Match completion behavior applies only to arena-type group chats. Verified Other group chats are unaffected by this logic.	0.5	Kinjal Shah	2025-06-04
	Call With CometChat		Call With CometChat	1	Jayesh Rathod	2025-06-03
	Call With CometChat		Call With CometChat	1	Pranay Prajapati	2025-06-03
Story	TD-256 -- AND - Step #9-1 -- Send Notification	https://tussly.atlassian.net/browse/TD-256	Verified that when a message is sent, a notification is triggered for the recipient. Tested that no notification is sent if the recipient is logged out. When the recipient’s app is in foreground, confirmed that an in-app notification is displayed. When the app is in the background, verified that a push notification appears in the app. Tested on both Android and iOS for system notification behavior. Verified notification content shows sender name and message preview correctly. Confirmed badge count are displayed properly on the app icon. Tested that the app does not crash during notification delivery failures. Confirmed that read status syncs after notification tap and chat screen opens.	0.75	Kinjal Shah	2025-06-03
Story	TD-262 -- AND - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-262	Verified long press on a message shows the Reply option. Confirmed tapping Reply opens a dedicated thread view screen. Tested that parent message is displayed at the top of the thread screen. Verified that replies are listed correctly below the parent message. Verified that replies are visible to all participants in real-time. Tested that the thread updates instantly on new incoming replies. Tested that real-time edit and delete changes in the thread. Verified user can edit their reply from the thread view. Confirmed edited replies update in real-time for all users. Verified user can delete their reply and it is removed from all views. Tested back navigation returns to main chat. Tested thread design separates parent and child messages clearly. Validated threaded replies persist across refresh and logout/login. Tested thread reply count shows accurately. Tested tapping reply count in main chat navigates to the correct thread.	1.25	Kinjal Shah	2025-06-03
Story	TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-254	Verified that Chat Icon is visible in Arena and clickable for all logged-in users. Confirmed user is navigated to Chat Message Screen if chat already exists. Verified "Contact Admin" button is visible on Chat Message Screen. Tested that if admin is not added,click on contact admin it will add the admin. Tested that if admin is already added, it will show the message that admin already added. Ensured admin chat is persistent across refresh/log out-log in scenarios. Ensured UI responsiveness and smooth screen transitions. Tested no duplicate chats are created. Tested that chat history loads correctly.	0.75	Kinjal Shah	2025-06-03
Story	TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat	https://tussly.atlassian.net/browse/TD-253	Verified that tapping the "Contact Admin" tab triggers a check for an existing chat conversation. And verified that if the chat exists, the user is navigated to the Chat Message Screen without delay. Verified that if the chat does not exist, the system initiates an API call to create a new chat with the admin. Tested that If the user is not logged in, confirmed that the system redirects them to the Login screen instead of initiating the chat flow. Ensured the chat screen loads recent messages smoothly once opened.	0.5	Kinjal Shah	2025-06-03
Bug	TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-292	Retest the bug in main and thread chat	0.17	Kinjal Shah	2025-06-03
Bug	TD-289-- Remove the Tost message	https://tussly.atlassian.net/browse/TD-289	Retest the bug	0.17	Kinjal Shah	2025-06-03
Bug	TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat	https://tussly.atlassian.net/browse/TD-279	Retest the bug	0.25	Kinjal Shah	2025-06-03
Bug	TD-369--Message Input Loses Focus After Sending in Chat	https://tussly.atlassian.net/browse/TD-369	Retest the bug	0.25	Kinjal Shah	2025-06-03
Bug	TD-362--Three-Dot Menu Overlaps with Message Layout	https://tussly.atlassian.net/browse/TD-362	Retest the bug	0.17	Kinjal Shah	2025-06-03
Bug	TD-273 -- Show the login and close button instead of ok	https://tussly.atlassian.net/browse/TD-273	Retest the bug	0.08	Kinjal Shah	2025-06-03
Bug	TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	https://tussly.atlassian.net/browse/TD-373	Retest the bug	0.17	Kinjal Shah	2025-06-03
Bug	TD-362--Three-Dot Menu Overlaps with Message Layout	https://tussly.atlassian.net/browse/TD-362	Changed the design to resolve the issue	2	Usama Shaikh	2025-06-03
Bug	TD-369--Message Input Loses Focus After Sending in Chat	https://tussly.atlassian.net/browse/TD-369	Resolved Bug	1	Usama Shaikh	2025-06-03
Bug	TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	https://tussly.atlassian.net/browse/TD-373	Remove chat from converstaion after leave the group	2	Usama Shaikh	2025-06-03
Bug	TD-354--Thread Replies Still Visible After Main Message Is Deleted	https://tussly.atlassian.net/browse/TD-354	Retest the bug	0.2	Kinjal Shah	2025-06-03
Bug	TD-360--New Message Not Sending After Editing a Previous Message	https://tussly.atlassian.net/browse/TD-360	Retest the bug	0.25	Kinjal Shah	2025-06-02
Story	TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	https://tussly.atlassian.net/browse/TD-359	Test the design in different device.	0.25	Kinjal Shah	2025-06-02
Bug	TD-357--Add the attachment functionality inside the thread.	https://tussly.atlassian.net/browse/TD-357	Test the attachment feature inside the thread.	0.25	Kinjal Shah	2025-06-02
Bug	TD-356--Edit Option Should Not Appear for Image and Document	https://tussly.atlassian.net/browse/TD-356	Retest the bug	0.17	Kinjal Shah	2025-06-02
Bug	TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	https://tussly.atlassian.net/browse/TD-355	Retest the bug	0.25	Kinjal Shah	2025-06-02
Bug	TD-352--Three-dot message menu does not close on outside click	https://tussly.atlassian.net/browse/TD-352	Retest the bug	0.17	Kinjal Shah	2025-06-02
Bug	TD-351--Increase Clickable Area for Document Download in Chat	https://tussly.atlassian.net/browse/TD-351	Retest the bug	0.17	Kinjal Shah	2025-06-02
Bug	TD-350--Set the Proper design	https://tussly.atlassian.net/browse/TD-350	Retest the bug	0.17	Kinjal Shah	2025-06-02
Bug	TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-348	Retest the bug	0.17	Kinjal Shah	2025-06-02
Bug	TD-342--Show the loader when attachment is sent	https://tussly.atlassian.net/browse/TD-342	Display loader.	0.33	Pranay Prajapati	2025-05-31
Story	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	https://tussly.atlassian.net/browse/TD-269	Verified that the Chat icon is visible for all logged-in users across the app. Confirmed that clicking the Chat icon navigates to the Chat list screen. Confirmed users can initiate new chats or continue existing ones without errors. Checked that timestamps are accurate for the last message in each conversation. Verified unread message badges are displayed correctly and update in real-time. Ensured the chat interface is responsive, adapting properly to various screen sizes.	1	Kinjal Shah	2025-05-31
Bug	TD-357--Add the attachment functionality inside the thread.	https://tussly.atlassian.net/browse/TD-357	Added the attachement functinallity in thread	4	Usama Shaikh	2025-05-31
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Verified that"Reply" option appears on click on three dots over a message. Tested that reply input links correctly to the main (parent) message. Checked that reply message appears in real-time across users. Verified reply count is shown below parent message. On clicking reply count, thread sidebar opens and loads related replies. Tested that main (parent) message is shown at the top of the thread view. Tested that thread messages support edit and delete functionality. Verified delivery and read receipts for threaded messages Tested that reply threads persist after page refresh or user logout/login. Tested that no duplicate message send on click.	0.75	Kinjal Shah	2025-05-31
Bug	TD-360--New Message Not Sending After Editing a Previous Message	https://tussly.atlassian.net/browse/TD-360	Resolved	1	Usama Shaikh	2025-05-31
Story	TD-217 -- Web - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-217	Verified that the Edit option appears on click on three dot on user’s own message. Tested that Edited message is successfully updated and displayed in the chat Confirmed that the edited message is updated in real-time for other users in the chat. Verified that edit is not available for messages with image/doc attachments, if restricted. Tested edited message is also updated correctly in thread view. Tested that after a message is edited, the user can send a new message without any issue.	0.58	Kinjal Shah	2025-05-31
Story	TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	https://tussly.atlassian.net/browse/TD-359	Designed the popup for leave group confirmation	2	Usama Shaikh	2025-05-31
Bug	TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-348	Prevetnt the clikc event when user send message & not send multiple message on reapeatedly hit enter	2	Usama Shaikh	2025-05-30
Bug	TD-350--Set the Proper design	https://tussly.atlassian.net/browse/TD-350	Resloved	0.5	Usama Shaikh	2025-05-30
Bug	TD-351--Increase Clickable Area for Document Download in Chat	https://tussly.atlassian.net/browse/TD-351	increased clickable area for download file	0.5	Usama Shaikh	2025-05-30
Bug	TD-352--Three-dot message menu does not close on outside click	https://tussly.atlassian.net/browse/TD-352	Closed option menu on outside clikc	1	Usama Shaikh	2025-05-30
Bug	TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	https://tussly.atlassian.net/browse/TD-353	Resolved	1	Usama Shaikh	2025-05-30
Bug	TD-354--Thread Replies Still Visible After Main Message Is Deleted	https://tussly.atlassian.net/browse/TD-354	Remove reply count under the bubblr after the deleted main message	0.5	Usama Shaikh	2025-05-30
Bug	TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	https://tussly.atlassian.net/browse/TD-355	set proper listner for Real time update edit & delete thread message	2	Usama Shaikh	2025-05-30
Bug	TD-356--Edit Option Should Not Appear for Image and Document	https://tussly.atlassian.net/browse/TD-356	Remove edit option from media message	0.5	Usama Shaikh	2025-05-30
Story	TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page	https://tussly.atlassian.net/browse/TD-216	Verified "Chat" button is visible on the Player Details page. Clicking the button opens an existing conversation if available. If no chat exists, a new chat is created. Verified that users can send and receive messages. Chat remains accessible after page refresh or logout/login. Checked loading indicators and smooth transition to chat screen.	0.25	Kinjal Shah	2025-05-30
Story	TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	https://tussly.atlassian.net/browse/TD-215	Verify that "Chat" button is visible next to each player and team in the list view. When user clicks "Chat", check for an existing conversation exist or not. If conversation exists → navigate to chat screen with loaded messages. If no conversation exists → create a new chat, then navigate to the screen. Tested that chat name, avatar, all details are accurate in new chat. Check for loading indicators while navigating or creating chat. Tested the chat with player and team. Verified that logging out from the web app successfully triggers the CometChat logout request.	0.5	Kinjal Shah	2025-05-30
Story	TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result	https://tussly.atlassian.net/browse/TD-214	Verify "Chat" button is visible for each match in Upcoming, Active, and Dispute tabs. On chat click, check navigation to chat group screen . Tested that navigate user to Group Chat Screen with correct participants. Tested that organizer can send messages to both players. Tested that players can reply. Verify that typing indicators,show correctly. Validate chat persists after refresh or logout-login.	0.25	Kinjal Shah	2025-05-30
Story	TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)	https://tussly.atlassian.net/browse/TD-213	Verified that the "Chat" button is visible next to each match in both Scheduled and Bracket sections. Clicked the "Chat" button for a match with an existing chat — confirmed that it navigates to the correct existing group chat. Tested that the organizer can send messages to both players within the chat. Tested that players can respond in the chat. Tested that Chat remains after a page refresh. Tested that Chat is still available after logging out and logging back in. Ensured no duplicate chat is created if the button is clicked multiple times rapidly.	0.33	Kinjal Shah	2025-05-30
Story	TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group	https://tussly.atlassian.net/browse/TD-212	Tested that “Leave Group” option is visible to admin in the Arena chat group. On clicking “Leave Group,” confirmed that the admin is removed from the group successfully. Ensured the group is no longer visible in the admin’s chat list after leaving. Checked that the admin no longer receives messages or notifications from the group. Validated that a system message is shown to remaining members indicating that the admin has left the group.	0.25	Kinjal Shah	2025-05-30
Story	TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens	https://tussly.atlassian.net/browse/TD-211	User clicks the Chat Icon from Scheduled or Scoreboards & Results section. Tested that If chat exists → user is redirected to the Group Chat screen. Tested If chat does not exist → new group chat is created, then user is navigated to the Group Chat screen. Tested that No duplicate chats are created on rapid/multiple clicks.	0.25	Kinjal Shah	2025-05-30
Story	TD-210 -- Web - Step #5-3 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-210	Tested that the typing indicator appears correctly when a user begins typing in a chat. Verified that the indicator automatically disappears after the user pauses typing for a few seconds. Confirmed that the typing indicator clears immediately once the user sends the message. Tested behavior when the recipient is offline, ensuring the typing indicator is shown once they reconnect. Checked that leaving the chat screen instantly clears the user’s typing status for the other participant.	0.33	Kinjal Shah	2025-05-30
Story	TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-207	Tested that messages are successfully sent and reflected in the chat interface. Tested that when the recipient opens the message, the sender's view reflects "Read" status. Tested tab switching and browser reloads to confirm that read status is preserved and correctly reflected. Tested that if the recipient was offline, messages update correctly once they come online and open the chat.	0.5	Kinjal Shah	2025-05-30
Story	TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-206	Verified that logging out from the web app successfully triggers the CometChat logout request. Confirmed that the logout was successful with no errors encountered during testing. No retry was required, as CometChat logout completed successfully on the first attempt. No error message was displayed, indicating that the logout process worked as intended.	0.17	Kinjal Shah	2025-05-30
Story	TD-346--Display Action Message in Chat	https://tussly.atlassian.net/browse/TD-346	Design new cell and display action message.	3	HasanAli	2025-05-29
Story	TD-347 -- iOS - Display Action Message in Chat	https://tussly.atlassian.net/browse/TD-347	Design new cell and display action message.	3	Pranay Prajapati	2025-05-29
	Crash App while open keyboard in Arena Chat		Solve crash issue.	0.75	Pranay Prajapati	2025-05-29
	SCRUM Meeting and Team Discussion		Meeting with developers, to display action message for show admin added or removed.	0.33	Jayesh Rathod	2025-05-29
Story	TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-207	Tapped the chat icon in the header and confirmed it redirects to the chat screen. Verified that if the user is logged into CometChat, existing conversations are displayed. Tested that if no conversations exist, a proper message like “No conversations yet” is shown. Tested that if user logout the app Access to chat is blocked. no chat icon will show and User is redirected to the login screen.	0.33	Kinjal Shah	2025-05-29
Story	TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-205	Verified that upon logging into Tussly, a ComentChat login is triggered automatically. Tested that when the Comet Chat login is successful, chat features are enabled. Tested that the system attempts to retry the Comet Chat login if it initially fails. Tested that chat features are only accessible when Comet Chat login is successful.	0.25	Kinjal Shah	2025-05-29
Story	TD-186 -- Web - Step #4-2 -- Logout from CometChat	https://tussly.atlassian.net/browse/TD-186	Tested that logging out of the web app triggers CometChat logout. Checked that on successful logout, the User is marked offline in chat. The user stops receiving messages and notifications. Validated that other users no longer see the logged-out user as "online" in chat.	0.5	Kinjal Shah	2025-05-29
Story	TD-185 -- Web - Step #4-1 -- Login to CometChat	https://tussly.atlassian.net/browse/TD-185	Tested that user is automatically logged into CometChat after successful app login. Confirmed that the user can access chat features immediately without needing to manually authenticate with CometChat. Tested that logging out of the app also logs the user out of CometChat seamlessly. Validated that login failures do not affect other parts of the application.	0.42	Kinjal Shah	2025-05-29
Story	TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members	https://tussly.atlassian.net/browse/TD-252	Tested that only team members are able to send and receive messages within the team chat. Tested the "Chat" tab on the Team Player Card. Confirmed non-team members are not allowed to chat. Validated logout scenarios to ensure redirection to the Login Screen when a logged-out user taps the chat tab. Ensured the team chat screen loads recent messages smoothly upon access. Tested the team chat functionality, sending multiple msg with media file and all.	0.5	Kinjal Shah	2025-05-28
Bug	TD-285-- Loader moves continuously not stop	https://tussly.atlassian.net/browse/TD-285	Solve the issue of Continuous moving loader in Realme Device.	1.5	HasanAli	2025-05-28
Bug	TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel	https://tussly.atlassian.net/browse/TD-341	Clear Edit text when cancel edit message in chat details page and also. in Thread reply page.	0.75	HasanAli	2025-05-28
Story	TD-261 -- AND - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-261	Tested the message edit flow by long-pressing a message to access the edit option. Verified that the updated message is sent via API and correctly replaces the original for all users. Tested the edit functionality after reopening the app from the background and after killing the app, ensuring the flow works seamlessly in both scenarios with proper real-time updates.	0.5	Kinjal Shah	2025-05-27
Story	TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-246	Verified that logging out from the app successfully triggers the CometChat logout request. Confirmed that the logout was successful with no errors encountered during testing. No retry was required, as CometChat logout completed successfully on the first attempt. No error message was displayed, indicating that the logout process worked as intended.	0.17	Kinjal Shah	2025-05-27
Bug	TD-340 -- IOS : Group chat scrolling is not working	https://tussly.atlassian.net/browse/TD-340	There is an problem with scroll layout while keyboard open, solve it.	3.5	Pranay Prajapati	2025-05-26
Story	TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat	https://tussly.atlassian.net/browse/TD-235	Verified that no push notification is sent when a user sends a message in a group chat by default. Tested that push notifications are sent correctly for one-to-one chats. Ensured that logged-out users do not receive any type of notifications.	0.33	Kinjal Shah	2025-05-26
Story	TD-257 -- AND - Step #9-2 -- Do Not Send Notifications for Group Chat	https://tussly.atlassian.net/browse/TD-257	Verified that no push notification is sent when a user sends a message in a group chat by default. Tested that push notifications are sent correctly for one-to-one chats. Ensured that logged-out users do not receive any type of notifications.	0.25	Kinjal Shah	2025-05-26
Story	TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-251	Verified that the chat correctly identifies whether it is a group chat or one-to-one chat. Verified that tapping the chat icon triggers an API call to fetch group chat details. Tested that when click on group conversation, the user is navigated to the Group Chat Message Screen. Tested the behavior when the user is logged out—ensuring they are redirected to the Login Screen. In group chats, confirmed that each message is displayed with the sender’s name and avatar.	0.25	Kinjal Shah	2025-05-26
Story	TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-229	Verified that the chat correctly identifies whether it is a group chat or one-to-one chat. Verified that tapping the chat icon triggers an API call to fetch group chat details. Tested that when click on group conversation, the user is navigated to the Group Chat Message Screen. Tested the behavior when the user is logged out—ensuring they are redirected to the Login Screen. In group chats, confirmed that each message is displayed with the sender’s name and avatar.	0.25	Kinjal Shah	2025-05-26
Story	TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-223	Verified that upon logging into Tussly, a ComentChat login is triggered automatically. Tested that when the Comet Chat login is successful, chat features are enabled and the user's presence updates to online. Tested that the system attempts to retry the Comet Chat login if it initially fails. Tested that chat features are only accessible when Comet Chat login is successful.	0.25	Kinjal Shah	2025-05-22
Bug	TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-294	While user enter and load all message then we read message and then update unread count.	0.75	Pranay Prajapati	2025-05-20
Story	TD-182 -- BE - Step #10 -- Notification Setup	https://tussly.atlassian.net/browse/TD-182	Conducted R&D on CometChat notifications and confirmed that message delivery and notifications are handled directly via the mobile app. Verified that the backend has no involvement in triggering or managing CometChat push notifications	3.5	Kishan Dharajiya	2025-05-19
Bug	TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	https://tussly.atlassian.net/browse/TD-293	Solve Unread Message count showing issue and test it.	1.5	HasanAli	2025-05-19
Story	TD-179 -- BE - Step #7 -- API to Identify Whether a User is a Friend or Not	https://tussly.atlassian.net/browse/TD-179	Created GET /api/user/:userId/is-friend API to check if the target user is a friend of the logged-in user. Implemented DB query, authentication, and tested with Postman and unit tests	3.5	Kishan Dharajiya	2025-05-16
Story	TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-245	Verified that upon logging into Tussly, a CometChat login is triggered automatically. Confirmed that when CometChat login is successful, chat features are enabled and the user's presence updates to online. Tested that if CometChat login fails, the user still has access to all non-chat features in Tussly. Verified that the system attempts to retry the CometChat login if it initially fails. Confirmed that chat features are only accessible when CometChat login is successful.	0.42	Kinjal Shah	2025-05-16
Story	TD-258 -- AND - Customization #2-1 -- Display Unread Message Count	https://tussly.atlassian.net/browse/TD-258	Verified that upon login, the API correctly fetches the unread message count and displays it as a count on the chat icon. Confirmed that the unread count updates in real time when a new message is received. Tested that when a user reads a message, the unread count decreases accordingly. Checked that the chat count disappears completely once all messages have been read.	0.58	Kinjal Shah	2025-05-16
Story	TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count	https://tussly.atlassian.net/browse/TD-236	Verified that upon login, the API correctly fetches the unread message count and displays it as a count on the chat icon. Confirmed that the unread count updates in real time when a new message is received. Tested that when a user reads a message, the unread count decreases accordingly. Checked that the chat count disappears completely once all messages have been read.	0.33	Kinjal Shah	2025-05-16
	SCRUM Meeting and Team Discussion		Meeting with developers, option for message edit, delete, an reply.	0.5	Jayesh Rathod	2025-05-16
Bug	TD-271 -- Display the same consistent message on iOS as shown on Android.	https://tussly.atlassian.net/browse/TD-271	Retest the bug check in new chat user	0.17	Kinjal Shah	2025-05-16
Bug	TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-291	Need to solve this whihle user tap multiple time while message sending to chat. Utill this time to send message disable send button.	1.33	Pranay Prajapati	2025-05-14
Bug	TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message	https://tussly.atlassian.net/browse/TD-290	This issue accure while load any image. While scroll is done then after UITableView set cell layout to display image proper. Solve this issue and then scroll to new message while enter in chat.	2.25	Pranay Prajapati	2025-05-14
Bug	TD-286 -- Unable to Delete Message from Reply Thread	https://tussly.atlassian.net/browse/TD-286	There is a problem with deleting text messages in the thread. Solve this, and make message delete work.	0.75	Pranay Prajapati	2025-05-14
Bug	TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button	https://tussly.atlassian.net/browse/TD-292	Solve multiple time send message issue in a Chat Details page and also solve in Thread Page.	2	HasanAli	2025-05-14
Bug	TD-289-- Remove the Tost message	https://tussly.atlassian.net/browse/TD-289	Remove Toast Message From All Screen.	0.5	HasanAli	2025-05-14
Story	TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App	https://tussly.atlassian.net/browse/TD-244	Tested the logout flow to ensure the user is automatically logged out of CometChat when logging out from the Android app. Tested that the user's CometChat presence is updated to offline after logout. Tested the user no longer receives messages or push notifications post logout. Tested online offline when logout from the app or in background mode.	0.5	Kinjal Shah	2025-05-14
Story	TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App	https://tussly.atlassian.net/browse/TD-222	Tested the logout flow to ensure the user is automatically logged out of CometChat when logging out from the iOS app. Tested that the user's CometChat presence is updated to offline after logout. Tested the user no longer receives messages or push notifications post logout. Tested online offline when logout from the app or in background mode.	0.5	Kinjal Shah	2025-05-14
Story	TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App	https://tussly.atlassian.net/browse/TD-243	Verified that user is automatically logged into CometChat after successfully logging into the app. Confirmed that the user can access chat features immediately without needing to manually authenticate with CometChat. Tested that logging out of the app also logs the user out of CometChat seamlessly.	0.25	Kinjal Shah	2025-05-14
Story	TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App	https://tussly.atlassian.net/browse/TD-221	Verified that user is automatically logged into CometChat after successfully logging into the app. Confirmed that the user can access chat features immediately without needing to manually authenticate with CometChat. Tested that logging out of the app also logs the user out of CometChat seamlessly.	0.25	Kinjal Shah	2025-05-14
Bug	TD-282 -- Edit Chat message is not working properly	https://tussly.atlassian.net/browse/TD-282	Get issue while user delete message. Need to manage while user delete message then update proper data and manage update cell based on it. Make proper edit message display in chat screen.	4	Pranay Prajapati	2025-05-13
Bug	TD-281 -- Showing Typing Indicator even when app is closed	https://tussly.atlassian.net/browse/TD-281	While kill application or send in background then typing not closed. Make it close.	0.5	Pranay Prajapati	2025-05-13
Bug	TD-271 -- Display the same consistent message on iOS as shown on Android.	https://tussly.atlassian.net/browse/TD-271	Message updated, given by client.	0.25	Pranay Prajapati	2025-05-13
Bug	TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	https://tussly.atlassian.net/browse/TD-278	Here issue with navigation stack. While user go in chat from teamCard and also from PlayerCard. Manage this navigation.	2	Pranay Prajapati	2025-05-13
Bug	TD-283 -- Showing Typing Indicator even when app is closed	https://tussly.atlassian.net/browse/TD-283	Solve the show Typing Indicator issue. when user kill the app then still showing typing.	3	HasanAli	2025-05-13
Story	TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	https://tussly.atlassian.net/browse/TD-215	Conversation not exist then creat conversation by sending “Hello” message & open the chat.	2	Usama Shaikh	2025-05-13
Story	TD-239 -- iOS - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-239	Tested the message edit flow by long-pressing a message to access the edit option. Verified that the updated message is sent via API and correctly replaces the original for all users. Tested the edit functionality after reopening the app from the background and after killing the app, ensuring the flow works seamlessly in both scenarios with proper real-time updates.	1	Kinjal Shah	2025-05-13
Story	TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality	https://tussly.atlassian.net/browse/TD-255	Tested the message deletion flow to ensure the delete option appears . Verified that deleted messages do not reappear after refresh or app relaunch. Tested that an after deleting message “This message was deleted” placeholder appears or not. Tested the message deletion flow after when app is open from background	0.5	Kinjal Shah	2025-05-13
Story	TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality	https://tussly.atlassian.net/browse/TD-233	Tested the message deletion flow to ensure the delete option appears . Verified that deleted messages do not reappear after refresh or app relaunch. Tested that an after deleting message “This message was deleted” placeholder appears or not. Tested the message deletion flow after when app is open from background	0.5	Kinjal Shah	2025-05-13
Story	TD-250 -- AND - Step #5-4 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-250	Tested that the typing indicator appears correctly when a user begins typing in a chat. Verified that the indicator automatically disappears after the user pauses typing for a few seconds. Confirmed that the typing indicator clears immediately once the user sends the message. Tested behavior when the recipient is offline, ensuring the typing indicator is shown once they reconnect. Checked that leaving the chat screen instantly clears the user’s typing status for the other participant. Tested the scenario where the user minimizes the app during typing—the indicator was properly cleared. Tested that if the app is killed while typing, the indicator disappears after a short timeout.	1	Kinjal Shah	2025-05-13
Story	TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-228	Tested that the typing indicator appears correctly when a user begins typing in a chat. Verified that the indicator automatically disappears after the user pauses typing for a few seconds. Confirmed that the typing indicator clears immediately once the user sends the message. Tested behavior when the recipient is offline, ensuring the typing indicator is shown once they reconnect. Checked that leaving the chat screen instantly clears the user’s typing status for the other participant. Tested the scenario where the user minimizes the app during typing—the indicator was properly cleared. Tested that if the app is killed while typing, the indicator disappears after a short timeout.	1	Kinjal Shah	2025-05-13
Bug	TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	https://tussly.atlassian.net/browse/TD-278	Here issue with navigation stack. While user go in chat from teamCard and also from PlayerCard. Manage this navigation. Working on it.	1	Pranay Prajapati	2025-05-12
Bug	TD-276 -- Chat Listing page should be refreshed.	https://tussly.atlassian.net/browse/TD-276	When app in background while chat list screen is open then all method and listener are closed. Manage this and reactive method and listener.	0.83	Pranay Prajapati	2025-05-12
Bug	TD-275 -- Chat page should be refreshed.	https://tussly.atlassian.net/browse/TD-275	When app in background while chat message screen is open then all method and listener are closed. Manage this and reactive method and listener.	0.75	Pranay Prajapati	2025-05-12
Bug	TD-272 -- IOS app crashes when clicking on chat	https://tussly.atlassian.net/browse/TD-272	Identify the crash issue and solve this from player card.	2	Pranay Prajapati	2025-05-12
Bug	TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.	https://tussly.atlassian.net/browse/TD-270	Update pop-up message appears while the user logs out.	0.25	Pranay Prajapati	2025-05-12
Story	TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page	https://tussly.atlassian.net/browse/TD-216	Open the personal chat in chat screen when conversation exist. Conversation not exist then creat conversation by sending “Hello” message & open the chat.	1	Usama Shaikh	2025-05-12
Story	TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	https://tussly.atlassian.net/browse/TD-215	Open the personal chat in chat screen when conversation exist.	2	Usama Shaikh	2025-05-12
Story	TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result	https://tussly.atlassian.net/browse/TD-214	Open the particular group which was added by the player to that group, otherwise call the API & enter the group & open that chat.	1	Usama Shaikh	2025-05-12
Story	TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)	https://tussly.atlassian.net/browse/TD-213	Open the particular group which was added by the player to that group, otherwise call the API & enter the group & open that chat.	1	Usama Shaikh	2025-05-12
Story	TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens	https://tussly.atlassian.net/browse/TD-211	Open Perticluar group when it's already added by player otherwies call the API & enter the group & open that	3	Usama Shaikh	2025-05-12
Bug	TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat	https://tussly.atlassian.net/browse/TD-279	Solve the UI issue when open a keyboard then chat list view is hide. and test it.	4	HasanAli	2025-05-12
Bug	TD-277 -- Chat Listing page should be refreshed.	https://tussly.atlassian.net/browse/TD-277	Page refreshed when app is open from background.	0.5	HasanAli	2025-05-12
Bug	TD-273 -- Show the login and close button instead of ok	https://tussly.atlassian.net/browse/TD-273	Update Popup Design and test it.	1	HasanAli	2025-05-12
Story	TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-249	Verified that messages are successfully sent and reflected in the chat interface. Confirmed that messages appear correctly on the recipient’s end after being sent. Validated that messages are marked as seen when the recipient opens the chat. Ensured that if the recipient was offline, messages update correctly once they come online and open the chat. Verified the message recipient when app is in background. Verified same read receipt feature in one to one player chat also.	1.5	Kinjal Shah	2025-05-12
Story	TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-227	Verified that messages are successfully sent and reflected in the chat interface. Confirmed that messages appear correctly on the recipient’s end after being sent. Validated that messages are marked as seen when the recipient opens the chat. Ensured that if the recipient was offline, messages update correctly once they come online and open the chat. Verified the message recipient when app is in background.Test the same read receipt feature in one to one player chat also. Test the same read receipt from friend list chat. Find issues and assign bug to the developer.	1.67	Kinjal Shah	2025-05-12
Story	TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-247	Confirmed that when the API response is successful, the user is navigated to the Chat Message Screen. Checked that if the user is not logged in, they are not able to open the chat screen. Tested that when the user is not logged in and taps the chat icon, a proper informational popup is displayed.	0.5	Kinjal Shah	2025-05-09
Story	TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-225	Confirmed that when the API response is successful, the user is navigated to the Chat Message Screen. Checked that if the user is not logged in, they are not able to open the chat screen. Tested that when the user is not logged in and taps the chat icon, a proper informational popup is displayed.	0.25	Kinjal Shah	2025-05-09
Story	TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-248	Verified that tapping the chat icon after login displays past conversations if available. Confirmed that when no past conversations exist, an appropriate message such as "No past conversations available" is displayed. Ensured the behavior is consistent across platforms and all user sessions.	0.42	Kinjal Shah	2025-05-09
Story	TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-226	Verified that tapping the chat icon after login displays past conversations if available. Confirmed that when no past conversations exist, an appropriate message such as "No past conversations available" is displayed. Ensured the behavior is consistent across platforms and all user sessions.	0.25	Kinjal Shah	2025-05-09
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Send Thread message	2	Usama Shaikh	2025-05-09
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Edit & Delete the thread message	1.5	Usama Shaikh	2025-05-09
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Addded Main Chat message to the Thread Message	1.5	Usama Shaikh	2025-05-09
Story	TD-262 -- AND - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-262	For reply. It’s works in thread. For this create new screen for reply in two part, first display parent message and , in second display replies. Here other options are available like edit and delete. Also active listener to get edited and deleted message same time.	3	HasanAli	2025-05-08
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Added Delivery & Read Receipet for the threaded message	2	Usama Shaikh	2025-05-08
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Loaded Thread mesage & set UI as per the chat	3	Usama Shaikh	2025-05-08
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	click on the reply count open thread message sidebar	2	Usama Shaikh	2025-05-08
Story	TD-218 -- Web - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-218	Show the Reply message count under the chat bubble	1	Usama Shaikh	2025-05-08
	SCRUM Meeting and Team Discussion		Meeting with developers, discuss about reply in message.	0.45	Jayesh Rathod	2025-05-08
Story	TD-262 -- AND - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-262	For reply. It’s works in thread. For this create new screen for reply in two part, first display parent message and , in second display replies. Here other options are available like edit and delete. Also active listener to get edited and deleted message same time.	5	HasanAli	2025-05-07
Story	TD-261 -- AND - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-261	For Edit message. Active long press on cell. For edit design new view to display edit message. And then user can edit message and then send to receiver that time update new message in place of previous message. Also active listener for get edited message from receiver.	3	HasanAli	2025-05-07
Story	TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat	https://tussly.atlassian.net/browse/TD-235	Check notification display for one to one, and not for group notification. But if group for arena match then send notification. Tried with manual code from app side but it's not working proper.	3	Pranay Prajapati	2025-05-07
Story	TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-207	Added MasrkAsread as reciepent & sender	2	Usama Shaikh	2025-05-07
Story	TD-210 -- Web - Step #5-3 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-210	Added typing indicator for group & user with real time	2	Usama Shaikh	2025-05-07
Story	TD-217 -- Web - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-217	Edited Message & real time update	4	Usama Shaikh	2025-05-07
Story	TD-261 -- AND - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-261	For Edit message. Active long press on cell. For edit design new view to display edit message. And then user can edit message and then send to receiver that time update new message in place of previous message. Also active listener for get edited message from receiver.	4	HasanAli	2025-05-06
Story	TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-260	Disable arena chat group after match finish. Set meta from backend to identify arena group chat. And after match finish then again update meta from backend then from application side manage to disable arena chat after match finish. And display Match Finish label.	4.25	HasanAli	2025-05-06
Story	TD-240 -- iOS - Customization -- Reply to Chat Message	https://tussly.atlassian.net/browse/TD-240	For reply. It’s works in thread. For this create new screen for reply in two part, first display parent message and , in second display replies. Here other options are available like edit and delete. Also active listener to get edited and deleted message same time.	8	Pranay Prajapati	2025-05-06
Story	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	https://tussly.atlassian.net/browse/TD-269	Added sticky Date & Responsive Design done	5	Usama Shaikh	2025-05-06
Story	TD-258 -- AND - Customization #2-1 -- Display Unread Message Count	https://tussly.atlassian.net/browse/TD-258	Update screen design to display unread count. Get method from CometChat and get unread count then display. There is an issue with unread count. We have contact CometChat Help, and will wait for a proper reply.	2.5	HasanAli	2025-05-05
Story	TD-256 -- AND - Step #9-1 -- Send Notification	https://tussly.atlassian.net/browse/TD-256	Notification for chat message. Setup notification configuration in application for CometChat. Configure notification in CometChat account, update firebase configuration.	2.5	HasanAli	2025-05-05
Story	TD-239 -- iOS - Customization -- Edit Chat Message	https://tussly.atlassian.net/browse/TD-239	For Edit message. Active long press on cell. For edit design new view to display edit message. And then user can edit message and then send to receiver that time update new message in place of previous message. Also active listener for get edited message from receiver.	7	Pranay Prajapati	2025-05-05
Story	TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-238	Disable arena chat group after match finish. Manage to disable arena chat after match finish. And display Match Finish label.	1	Pranay Prajapati	2025-05-05
Story	TD-181 -- BE - Step #9 -- Manage Flag for Disabling Chat	https://tussly.atlassian.net/browse/TD-181	Update match group metadata while match complete, manually update match, forfeit match	3	Kishan Dharajiya	2025-05-05
Story	TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	https://tussly.atlassian.net/browse/TD-238	Disable arena chat group after match finish. Set meta from backend to identify arena group chat. And after match finish then again update meta from backend then from application side manage to disable arena chat after match finish. And display Match Finish label.	3.5	Pranay Prajapati	2025-05-02
Story	TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count	https://tussly.atlassian.net/browse/TD-236	Update screen design to display unread count. Get method from CometChat and get unread count then display. There is an issue with unread count. We have contact CometChat Help, and will wait for a proper reply.	1.83	Pranay Prajapati	2025-05-02
Story	TD-234 -- iOS - Step #9-1 -- Send Notification	https://tussly.atlassian.net/browse/TD-234	Notification for chat message. Setup notification configuration in application for CometChat. Configure notification in CometChat account, update firebase configuration. Get some issue in getting notifications. Solve it.	2.75	Pranay Prajapati	2025-05-02
Story	TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat	https://tussly.atlassian.net/browse/TD-180	Create API for remove organizer Implemented removeOrganizer(matchId, userId) function.	2	Kishan Dharajiya	2025-05-02
Story	TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat	https://tussly.atlassian.net/browse/TD-180	Create API for add organizer into the match Group Developed addOrganizer(matchId, userId) function.	2	Kishan Dharajiya	2025-05-02
Story	TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality	https://tussly.atlassian.net/browse/TD-255	For Delete message. Update cell design for message delete. Activate long press, and on long press display option for message. On delete tap, call cometchat method for delete message. On delete success, update cell and remove delete message and display message deleted.	3.8	HasanAli	2025-05-01
Story	TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-254	Working on chat in arena. Update API for get chat id based on match. Then pass chat id on click on chat icon tap and open chat between two player. Here I need to manage arena timer and flow while open chat from arena. Design button for ‘Add Admin'. On click add admin then call API for add admin, on success admin added to arena chat. Here Add meta from backend for identify this chat group is for arena match. So from chat list we can identify it’s arena match group. After match finish disable chat in arena match group.	4	HasanAli	2025-05-01
Story	TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality	https://tussly.atlassian.net/browse/TD-233	For Delete message. Update cell design for message delete. Activate long press, and on long press display option for message. On delete tap, call cometchat method for delete message. On delete success, update cell and remove delete message and display message deleted.	4	Pranay Prajapati	2025-05-01
Story	TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-232	Working on chat in arena. Here Add meta from backend for identify this chhat group is for arena match. So from chat list we can identify it’s arena match group. After match finish disable chat in arena match group.	4	Pranay Prajapati	2025-05-01
Story	TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group	https://tussly.atlassian.net/browse/TD-212	Admin Can leave the group afrter calling Bakcend API response	1.5	Usama Shaikh	2025-05-01
Story	TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-207	Added Chat Icon in header for got to the chat screen	1	Usama Shaikh	2025-05-01
Story	TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-254	Working on chat in arena. Update API for get chat id based on match. Then pass chat id on click on chat icon tap and open chat between two player. Here I need to manage arena timer and flow while open chat from arena. Design button for ‘Add Admin'. On click add admin then call API for add admin, on success admin added to arena chat. Here Add meta from backend for identify this chat group is for arena match. So from chat list we can identify it’s arena match group. After match finish disable chat in arena match group.	8	HasanAli	2025-04-30
Story	TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	https://tussly.atlassian.net/browse/TD-232	Working on chat in arena. Update API for get chat id based on match. Then pass chat id on click on chat icon tap and open chat between two player. Here I need to manage arena timer and flow while open chat from arena. Design button for ‘Add Admin'. On click add admin then call API for add admin, on success admin added to arena chat.	8	Pranay Prajapati	2025-04-30
Story	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	https://tussly.atlassian.net/browse/TD-269	Added CometChatSDK for the conversation list & Messsgae	3	Usama Shaikh	2025-04-30
Story	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	https://tussly.atlassian.net/browse/TD-269	Design Message panel	3	Usama Shaikh	2025-04-30
Story	TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players	https://tussly.atlassian.net/browse/TD-178	Updated Metadata on Match Completion Details: Triggered on match status = completed. Updated CometChat group metadata (status: completed, endedAt). Also exposed manualMetadataUpdate(matchId, data) for admin edits.	4	Kishan Dharajiya	2025-04-30
Story	TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat	https://tussly.atlassian.net/browse/TD-253	Here player chat with tourament admin/organizer. When player go to tournament details page. Contact admin, while tap on tab then open chat between admin and player.	3	HasanAli	2025-04-29
Story	TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members	https://tussly.atlassian.net/browse/TD-252	In team page, icon for group chat. Get required value from backend and then pass value to comet chat and retrieve past conversation messages and make all listener active and chat to group members.	3.3	HasanAli	2025-04-29
Story	TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat	https://tussly.atlassian.net/browse/TD-231	Here player ca chat with tourament admin/organizer. When player go to tournament details page. Contact admin, while tap on tab then open chat between admin and player.	2.75	Pranay Prajapati	2025-04-29
Story	TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members	https://tussly.atlassian.net/browse/TD-230	In team page, icon for group chat. Get required value from backend and then pass value to comet chat and retrieve past conversation messages and make all listener active and chat to group members.	3.25	Pranay Prajapati	2025-04-29
Story	TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-229	Get required value from backend and then pass value to comet chat and retrieve past group conversation messages if available ad display to tv and make all listener active like messag listener to real time message, typing, message read and chat to group members.	2	Pranay Prajapati	2025-04-29
Story	TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players	https://tussly.atlassian.net/browse/TD-178	Created Match Group with Participants Details: Built createMatchGroup(matchId, participantIds) method. Generated unique groupId using match_{matchId}. Added participants as CometChat members with participant scope. Stored group metadata (matchId, status, timestamps) in the database.	4.5	Kishan Dharajiya	2025-04-29
Story	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	https://tussly.atlassian.net/browse/TD-269	Desing the chat screen for the converstion list (Pending)	2.5	Usama Shaikh	2025-04-29
Story	TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-206	Added logout failure message	1	Usama Shaikh	2025-04-29
Story	TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-205	Added Login faliure with Toaster & disabled the chat	3	Usama Shaikh	2025-04-29
Story	TD-177 -- BE - Step #5 -- Register User in CometChat Upon Signup	https://tussly.atlassian.net/browse/TD-177	Create a unified function to register, login (social/signup), update user details (edit profile), upload profile picture, and sync user data with CometChat for both new and existing users.	3	Kishan Dharajiya	2025-04-29
Story	TD-268 -- BE - Step #4A -- Sync All the old teams	https://tussly.atlassian.net/browse/TD-268	Create a command for sync the old teams With member and make the admin who is the founder of the team,	2	Kishan Dharajiya	2025-04-29
Story	TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-251	Identify group chat or one to one. In group chat display other user message with name and avatar. Get required value from backend and then pass value to comet chat and retrieve past group conversation messages and make all listener active and chat to group members.	3	HasanAli	2025-04-28
Story	TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-251	Identify group chat or one to one. In group chat display other user message with name and avatar. Get required value from backend and then pass value to comet chat and retrieve past group conversation messages and make all listener active and chat to group members.	2.8	HasanAli	2025-04-28
Story	TD-250 -- AND - Step #5-4 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-250	Here, while user typing call comet chat method to make user typig and then make typing off. Active listener for typing and not typing based on comet chat method call get value for typing or not.	2	HasanAli	2025-04-28
Story	TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-249	Update cell design for display read receipt. Then active listener to message read or not. When message arrive then mark as read.	2.35	HasanAli	2025-04-28
Story	TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-229	Identify group chat or one to one. In group chat display other user message with name and avatar.	1	Pranay Prajapati	2025-04-28
Story	TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators	https://tussly.atlassian.net/browse/TD-228	Here, while user typing call comet chat method to make user typig and then make typing off. Active listener for typing and not typing based on comet chhat method call get value for typing or not.	2	Pranay Prajapati	2025-04-28
Story	TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature	https://tussly.atlassian.net/browse/TD-227	Update cell design for display read receipt. Then active listener to message read or not. When message arrive then mark as read.	2.5	Pranay Prajapati	2025-04-28
Story	TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-226	Get Message list if available previous chat. Then display message to tv. Design date separator label for message. When scroll message display date on top.	2.5	Pranay Prajapati	2025-04-28
Story	TD-186 -- Web - Step #4-2 -- Logout from CometChat	https://tussly.atlassian.net/browse/TD-186	On app logout, we call CometChat.logout() to immediately terminate the user’s chat session in sync with their sign-out & tested	1.5	Usama Shaikh	2025-04-28
Story	TD-185 -- Web - Step #4-1 -- Login to CometChat	https://tussly.atlassian.net/browse/TD-185	CometChat now automatically authenticates users on app login (with one retry on transient errors), enables chat on success, disables it and notifies on failure, and syncs logout seamlessly.	1.5	Usama Shaikh	2025-04-28
Story	TD-184 -- Web - Step #3-2 -- Initialize CometChat SDK	https://tussly.atlassian.net/browse/TD-184	CometChat now automatically authenticates users on app login using their unique ID (with one retry on transient failures), enables chat on success, disables it and shows an error notification on failure, and syncs logout behavior seamlessly.	2	Usama Shaikh	2025-04-28
Story	TD-183 -- Web - Step #3-1 -- Integrate CometChat SDK	https://tussly.atlassian.net/browse/TD-183	CometChat Web SDK is now fully integrated—providing secure, real-time chat with authentication guards and robust error handling.	2	Usama Shaikh	2025-04-28
Story	TD-268 -- BE - Step #4A -- Sync All the old teams	https://tussly.atlassian.net/browse/TD-268	"Group created successfully with all members added." "Group and members have been created and linked successfully." "New group created. All selected members are now part of the group."	3	Kishan Dharajiya	2025-04-28
Story	TD-176 -- BE - Step #4 -- Sync All Old App Users	https://tussly.atlassian.net/browse/TD-176	A common function to create users in CometChat. A command (probably a script/command file) to sync old users. Avoid duplicate creation (check if the user exists first). Retry up to 3 times if user creation fails.	3.5	Kishan Dharajiya	2025-04-28
Story	TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-248	Now in Chat List screen. Design chat list screen, design Cell for chat list. On conversation tap, go into chat message screen. Get message list from comet chat. Aftre design screen and cell for display message. Active listener to get real time message update.	5.5	HasanAli	2025-04-25
Story	TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-247	Now on tap on the chat icon then navigate to Chat List screen.	2.7	HasanAli	2025-04-25
Story	TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-246	Implement logout in CometChat. If any issue occurs, handle it and try again to log out of Cometchat. After trying again, get the issue, and then continue to log out to Tussly.	2.3	HasanAli	2025-04-25
Story	TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App	https://tussly.atlassian.net/browse/TD-243	After Initialization, implement login in CometChat.	1.9	HasanAli	2025-04-25
Story	TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations	https://tussly.atlassian.net/browse/TD-226	Design Cell for display image for sender and receiver. Design document cell for sender and receiver.	3	Pranay Prajapati	2025-04-25
	SCRUM Meeting and Team Discussion		Meting with team, to discuss about ChatList and ChatMessageVC	0.5	Jayesh Rathod	2025-04-25
Story	TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap	https://tussly.atlassian.net/browse/TD-225	Now on tap on the chat icon then navigate to Chat List screen. Chat List screen. Design chat list screen, design TV Cell for chat list. Fetch data from comet chat and display.	2.5	Pranay Prajapati	2025-04-25
Story	TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure	https://tussly.atlassian.net/browse/TD-224	Implement logout in CometChat. If any issue occurs, handle it and try again to log out of Cometchat. After trying again, get the issue, and then continue to log out to Tussly.	2.5	Pranay Prajapati	2025-04-25
Story	TD-176 -- BE - Step #4 -- Sync All Old App Users	https://tussly.atlassian.net/browse/TD-176	Create a common function to handle user creation in CometChat.	2	Kishan Dharajiya	2025-04-25
Story	TD-175 -- BE - Step #3 -- Integrate CometChat SDK	https://tussly.atlassian.net/browse/TD-175	Create CometChat Helper Class & Make guzzle call from every API request	1.5	Kishan Dharajiya	2025-04-25
Story	TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-245	Implement login in CometChat. If any issue occurs, then handle that and try again to log in to Cometchat. After trying again, get the issue, then continue to log in to Tussly.	2.5	HasanAli	2025-04-24
Story	TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App	https://tussly.atlassian.net/browse/TD-244	After Initialization, implement logout from CometChat.	1.8	HasanAli	2025-04-24
Story	TD-242 -- AND - Step #3-2 -- Initialize CometChat SDK	https://tussly.atlassian.net/browse/TD-242	Initialize CometChat SDK in Tussly.	2	HasanAli	2025-04-24
Story	TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure	https://tussly.atlassian.net/browse/TD-223	Implement login in CometChat. If any issue occurs, then handle that and try again to log in to Cometchat. After trying again, get the issue, then continue to log in to Tussly.	2.33	Pranay Prajapati	2025-04-24
Story	TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App	https://tussly.atlassian.net/browse/TD-222	After Initialization, implement logout from CometChat.	1.83	Pranay Prajapati	2025-04-24
Story	TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App	https://tussly.atlassian.net/browse/TD-221	After Initialization, implement login in CometChat. Get issue while login CometChat. Solve issue and login CometChat.	1.83	Pranay Prajapati	2025-04-24
Story	TD-220 -- iOS - Step #3-2 -- Initialize CometChat SDK	https://tussly.atlassian.net/browse/TD-220	Initialize CometChat SDK in Tussly	2	Pranay Prajapati	2025-04-24
Story	TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)	https://tussly.atlassian.net/browse/TD-174	Create Tussly Live app on cometChat & provide the credential to the team	1	Kishan Dharajiya	2025-04-24
Story	TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)	https://tussly.atlassian.net/browse/TD-174	Create Tussly staging app on cometChat & provide the credential to the team	1.5	Kishan Dharajiya	2025-04-24
Story	TD-219 -- iOS - Step #3-1 -- Integrate CometChat SDK	https://tussly.atlassian.net/browse/TD-219	Integrate ComeChat SDK Get issue while integrate comet chat using pod. Issue solved.	2.83	Pranay Prajapati	2025-04-23
	SCRUM Meeting and Team Discussion		Meeting with developers to work on CometChat integration across iOS, Android, Web, and Backend.	0.33	Jayesh Rathod	2025-04-23
	Check and Update Sprint 5 Task Estimate		Check and Update Sprint 5 Task Estimate	2.5	Jayesh Rathod	2025-04-09
	Working on Action Item & Update Task/Story		Working on Action Item & Update Task/Story	1.75	Jayesh Rathod	2025-04-03
	Jira – Confluence Page and Task Create		Jira – Confluence Page and Task Create	5.75	Jayesh Rathod	2025-03-28
	Jira – Confluence Page and Task Create		Jira – Confluence Page and Task Create	4	Jayesh Rathod	2025-03-27

				435.33

## All_Log
Item	Estimation	Jayesh Rathod	Kishan Dharajiya	Usama Shaikh	Pranay Prajapati	HasanAli	Kinjal Shah	Spent Hours	Difference
Jira – Confluence Page and Task Create	9.75	9.75	0	0	0	0	0	9.75	0
Working on Action Item & Update Task/Story	1.75	1.75	0	0	0	0	0	1.75	0
Check and Update Sprint 5 Task Estimate	2.5	2.5	0	0	0	0	0	2.5	0
Call With CometChat	6	3	0	0	3	0	0	6	0
SCRUM Meeting and Team Discussion	2.11	2.11	0	0	0	0	0	2.11	0
TD-387--IOS: Notification delay	1.5	0	0	0	1.5	0	0	1.5	0
TD-282 -- Edit Chat message is not working properly	4.45	0	0	0	4	0	0.42	4.42	0.0300000000000003
TD-339-- IOS : Received notification in the group chat	0.5	0	0	0	0.33	0	0.17	0.5	0
TD-386--Notification click redirection	1.5	0	0	0	1.5	0	0.25	1.75	-0.25
TD-349--User shows as online even when user is closed or logout	1.2	0	0	1	0	0	0.17	1.17	0.03
TD-280 -- User shows as online even when app is closed or in background	0.5	0	0	0	0.17	0	0.33	0.5	0
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	3.33	0	0	0	3	0	0.33	3.33	0
TD-281 -- Showing Typing Indicator even when app is closed	0.67	0	0	0	0.5	0	0.17	0.67	0
TD-272 -- IOS app crashes when clicking on chat	2.17	0	0	0	2	0	0.17	2.17	0
TD-275 -- Chat page should be refreshed.	0.92	0	0	0	0.75	0	0.17	0.92	0
TD-340 -- IOS : Group chat scrolling is not working	3.67	0	0	0	3.5	0	0.17	3.67	0
TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message	2.5	0	0	0	2.25	0	0.25	2.5	0
TD-276 -- Chat Listing page should be refreshed.	1	0	0	0	0.83	0	0.17	1	0
TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.	0.33	0	0	0	0.25	0	0.08	0.33	0
TD-286 -- Unable to Delete Message from Reply Thread	0.95	0	0	0	0.75	0	0.2	0.95	0
TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button	1.5	0	0	0	1.33	0	0.17	1.5	0
TD-342--Show the loader when attachment is sent	0.5	0	0	0	0.33	0	0.17	0.5	0
TD-347 -- iOS - Display Action Message in Chat	3	0	0	0	3	0	0.33	3.33	-0.33
TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	1.12	0	0	1	0	0	0.12	1.12	0
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	1.75	0	0	0	0	1.5	0.42	1.92	-0.17
TD-283 -- Showing Typing Indicator even when app is closed	3.33	0	0	0	0	3	0.33	3.33	0
TD-277 -- Chat Listing page should be refreshed.	0.75	0	0	0	0	0.5	0.25	0.75	0
TD-285-- Loader moves continuously not stop	1.75	0	0	0	0	1.5	0.25	1.75	0
TD-346--Display Action Message in Chat	3	0	0	0	0	3	0.33	3.33	-0.33
TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel	0.95	0	0	0	0	0.75	0.2	0.95	0
TD-343--Android: Show the loader when attachment is sent	0.17	0	0	0	0	0	0.17	0.17	0
TD-284 -- Application is crashed when delete the message.	0.17	0	0	0	0.17	0	0.17	0.34	-0.17
TD-240 -- iOS - Customization -- Reply to Chat Message	7.5	0	0	0	8	0	1.17	9.17	-1.67
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	4.5	0	0	0	4.5	0	0.42	4.92	-0.42
TD-234 -- iOS - Step #9-1 -- Send Notification	3	0	0	0	2.75	0	0.58	3.33	-0.33
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	12	0	0	0	12	0	0.58	12.58	-0.58
TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat	3	0	0	0	2.75	0	0.5	3.25	-0.25
TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members	3.5	0	0	0	3.25	0	0.5	3.75	-0.25
TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure	2.5	0	0	0	2.5	0	0.25	2.75	-0.25
TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion	4.5	0	0	0	0	4.25	0.5	4.75	-0.25
TD-256 -- AND - Step #9-1 -- Send Notification	3	0	0	0	0	2.5	0.75	3.25	-0.25
TD-262 -- AND - Customization -- Reply to Chat Message	7.5	0	0	0	0	8	1.25	9.25	-1.75
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	12	0	0	0	0	12	0.75	12.75	-0.75
TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat	3	0	0	0	0	3	0.5	3.5	-0.5
TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button	2.2	0	0	0	0	2	0.17	2.17	0.0300000000000003
TD-289-- Remove the Tost message	0.67	0	0	0	0	0.5	0.17	0.67	0
TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat	2.5	0	0	0	0	4	0.25	4.25	-1.75
TD-369--Message Input Loses Focus After Sending in Chat	1.25	0	0	1	0	0	0.25	1.25	0
TD-362--Three-Dot Menu Overlaps with Message Layout	2.17	0	0	2	0	0	0.17	2.17	0
TD-273 -- Show the login and close button instead of ok	1.1	0	0	0	0	1	0.08	1.08	0.02
TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	2.17	0	0	2	0	0	0.17	2.17	0
TD-354--Thread Replies Still Visible After Main Message Is Deleted	0.7	0	0	0.5	0	0	0.2	0.7	0
TD-360--New Message Not Sending After Editing a Previous Message	1.25	0	0	1	0	0	0.25	1.25	0
TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	2.25	0	0	2	0	0	0.25	2.25	0
TD-357--Add the attachment functionality inside the thread.	4.25	0	0	4	0	0	0.25	4.25	0
TD-356--Edit Option Should Not Appear for Image and Document	0.67	0	0	0.5	0	0	0.17	0.67	0
TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	2.25	0	0	2	0	0	0.25	2.25	0
TD-352--Three-dot message menu does not close on outside click	1.17	0	0	1	0	0	0.17	1.17	0
TD-351--Increase Clickable Area for Document Download in Chat	0.67	0	0	0.5	0	0	0.17	0.67	0
TD-350--Set the Proper design	0.67	0	0	0.5	0	0	0.17	0.67	0
TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	2.17	0	0	2	0	0	0.17	2.17	0
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	16	0	0	13.5	0	0	1	14.5	1.5
TD-218 -- Web - Customization -- Reply to Chat Message	14	0	0	13	0	0	0.75	13.75	0.25
TD-217 -- Web - Customization -- Edit Chat Message	2	0	0	4	0	0	0.58	4.58	-2.58
TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result	1	0	0	1	0	0	0.25	1.25	-0.25
TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)	1	0	0	1	0	0	0.33	1.33	-0.33
TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group	2	0	0	1.5	0	0	0.25	1.75	0.25
TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens	2	0	0	3	0	0	0.25	3.25	-1.25
TD-210 -- Web - Step #5-3 -- Implement Typing Indicators	2	0	0	2	0	0	0.33	2.33	-0.33
TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	2	0	0	2	0	0	0.5	2.5	-0.5
TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure	3	0	0	1	0	0	0.17	1.17	1.83
TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure	3	0	0	3	0	0	0.25	3.25	-0.25
TD-186 -- Web - Step #4-2 -- Logout from CometChat	2	0	0	1.5	0	0	0.5	2	0
TD-185 -- Web - Step #4-1 -- Login to CometChat	3	0	0	1.5	0	0	0.42	1.92	1.08
TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members	3.5	0	0	0	0	3.3	0.5	3.8	-0.3
TD-261 -- AND - Customization -- Edit Chat Message	7	0	0	0	0	7	0.5	7.5	-0.5
TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure	2.5	0	0	0	0	2.3	0.17	2.47	0.0300000000000003
TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat	3.33	0	0	0	3	0	0.33	3.33	0
TD-257 -- AND - Step #9-2 -- Do Not Send Notifications for Group Chat	0.25	0	0	0	0	0	0.25	0.25	0
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	3	0	0	0	0	5.8	0.25	6.05	-3.05
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	3	0	0	0	3	0	0.25	3.25	-0.25
TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure	2.5	0	0	0	2.33	0	0.25	2.58	-0.0800000000000001
TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages	0.75	0	0	0	0.75	0	0.17	0.92	-0.17
TD-182 -- BE - Step #10 -- Notification Setup	8	0	3.5	0	0	0	0	3.5	4.5
TD-179 -- BE - Step #7 -- API to Identify Whether a User is a Friend or Not	4	0	3.5	0	0	0	0	3.5	0.5
TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure	2.5	0	0	0	0	2.5	0.42	2.92	-0.42
TD-258 -- AND - Customization #2-1 -- Display Unread Message Count	2	0	0	0	0	2.5	0.58	3.08	-1.08
TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count	2	0	0	0	1.83	0	0.33	2.16	-0.16
TD-271 -- Display the same consistent message on iOS as shown on Android.	0	0	0	0	0.25	0	0.17	0.42	-0.42
TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App	2	0	0	0	0	1.8	0.5	2.3	-0.3
TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App	2	0	0	0	1.83	0	0.5	2.33	-0.33
TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App	2	0	0	0	0	1.9	0.25	2.15	-0.15
TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App	2	0	0	0	1.83	0	0.25	2.08	-0.0800000000000001
TD-250 -- AND - Step #5-4 -- Implement Typing Indicators	2	0	0	0	0	2	1	3	-1
TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators	2	0	0	0	2	0	1	3	-1
TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature	2.5	0	0	0	0	2.35	1.5	3.85	-1.35
TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature	2.5	0	0	0	2.5	0	1.67	4.17	-1.67
TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap	2.5	0	0	0	0	2.7	0.5	3.2	-0.7
TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap	2.5	0	0	0	2.5	0	0.25	2.75	-0.25
TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations	5.33	0	0	0	0	5.5	0.42	5.92	-0.59
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations	5.33	0	0	0	5.5	0	0.25	5.75	-0.42
TD-181 -- BE - Step #9 -- Manage Flag for Disabling Chat	3	0	3	0	0	0	0	3	0
TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat	4	0	4	0	0	0	0	4	0
TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players	12	0	8.5	0	0	0	0	8.5	3.5
TD-177 -- BE - Step #5 -- Register User in CometChat Upon Signup	3	0	3	0	0	0	0	3	0
TD-268 -- BE - Step #4A -- Sync All the old teams	5	0	5	0	0	0	0	5	0
TD-184 -- Web - Step #3-2 -- Initialize CometChat SDK	2	0	0	2	0	0	0	2	0
TD-183 -- Web - Step #3-1 -- Integrate CometChat SDK	3	0	0	2	0	0	0	2	1
TD-176 -- BE - Step #4 -- Sync All Old App Users	7	0	5.5	0	0	0	0	5.5	1.5
TD-175 -- BE - Step #3 -- Integrate CometChat SDK	2	0	1.5	0	0	0	0	1.5	0.5
TD-242 -- AND - Step #3-2 -- Initialize CometChat SDK	2	0	0	0	0	2	0	2	0
TD-220 -- iOS - Step #3-2 -- Initialize CometChat SDK	2	0	0	0	2	0	0	2	0
TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)	4	0	2.5	0	0	0	0	2.5	1.5
TD-219 -- iOS - Step #3-1 -- Integrate CometChat SDK	3	0	0	0	2.83	0	0	2.83	0.17
TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page	1	0	0	1	0	0	0.25	1.25	-0.25
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	1	0	0	4	0	0	0.5	4.5	-3.5
TD-239 -- iOS - Customization -- Edit Chat Message	7	0	0	0	7	0	1	8	-1
TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality	4	0	0	0	0	3.8	0.5	4.3	-0.3
TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality	4	0	0	0	4	0	0.5	4.5	-0.5
TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap	2	0	0	1	0	0	0.33	1.33	0.67
Crash App while open keyboard in Arena Chat	0.75	0	0	0	0.75	0	0	0.75	0
TD-385--Notification click redirection	0.25	0	0	0	0	0	0.25	0.25	0
TD-405 -- Web - Enable or Implement “Invite via Link” Functionality on Team Page	1	0	0	1	0	0	0	1	0
TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	8.5	0	0	0	8.5	0	0	8.5	0
TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	8	0	0	0	8	0	0	8	0
TD-428 -- AND - App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	5	0	0	0	0	5	0	5	0
TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	2.25	0	0	2	0	0	0.25	2.25	0
TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	2.33	0	0	2	0	0	0.33	2.33	0
TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	1.25	0	0	1	0	0	0.25	1.25	0
TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	1.17	0	0	0	1	0	0.17	1.17	0
TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	4.25	0	0	0	4	0	0.25	4.25	0
TD-411 -- iOS - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	3	0	0	0	3	0	0	3	0
TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	1.17	0	0	0	0	1	0.17	1.17	0
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	1.42	0	0	0	0	1	0.42	1.42	0
TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	1	0	0	0	0	0.75	0.25	1	0
TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	2.17	0	0	0	0	2	0.17	2.17	0
TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	0.42	0	0	0	0.17	0	0.25	0.42	0
TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	0.34	0	0	0	0.17	0	0.17	0.34	0
TD-420 -- iOS Users Do Not Receive First Message from Organizer in Arena Chat	2	0	0	0	2	0	0	2	0
TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	3.33	0	0	0	3	0	0.33	3.33	0
TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	3.17	0	0	0	2.67	0	0.5	3.17	0
TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	2.5	0	0	0	2.25	0	0.25	2.5	0
TD-410 -- Dismiss Keyboard on Outside Tap	3	0	0	0	3	0	0	3	0

	418.66	19.11	40	85	146.57	102.7	41.95	435.33	-16.67

## Sheet4
Item	Item
Call With CometChat	Call With CometChat	6
Call With CometChat	TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	3.17			#N/A
TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	TD-410 -- Dismiss Keyboard on Outside Tap	3
TD-410 -- Dismiss Keyboard on Outside Tap	TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	2.33
TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	1.25
TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	2.25
TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	3.33
TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	1.17
TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	4.25
TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	2.5
TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	2.17
TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	1.42
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	0.34
TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	0.42
TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	1.17
TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	1
TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	TD-420 -- iOS Users Do Not Receive First Message from Organizer in Arena Chat	2
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	TD-411 -- iOS - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	3
TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	TD-428 -- AND - App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	5
TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync	TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	8
TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt	TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	8.5
TD-420 -- iOS Users Do Not Receive First Message from Organizer in Arena Chat	TD-405 -- Web - Enable or Implement “Invite via Link” Functionality on Team Page	1
TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read	TD-386--Notification click redirection	1.75
TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)	TD-385--Notification click redirection	0.25
TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages	0.92
TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging	TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	1.92
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon	TD-284 -- Application is crashed when delete the message.	0.34
TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	TD-387--IOS: Notification delay	1.5
TD-411 -- iOS - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync	TD-282 -- Edit Chat message is not working properly	4.42
TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon	TD-339-- IOS : Received notification in the group chat	0.5
TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat	TD-349--User shows as online even when user is closed or logout	1.17
TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section	TD-280 -- User shows as online even when app is closed or in background	0.5
TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players	TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	3.33
TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support	TD-281 -- Showing Typing Indicator even when app is closed	0.67
TD-428 -- AND - App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	TD-272 -- IOS app crashes when clicking on chat	2.17
TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	TD-275 -- Chat page should be refreshed.	0.92
TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	TD-340 -- IOS : Group chat scrolling is not working	3.67
TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging	TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message	2.5
TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)	TD-276 -- Chat Listing page should be refreshed.	1
TD-405 -- Web - Enable or Implement “Invite via Link” Functionality on Team Page	TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.	0.33
TD-386--Notification click redirection	TD-286 -- Unable to Delete Message from Reply Thread	0.95
TD-385--Notification click redirection	TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button	1.5
TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages	TD-342--Show the loader when attachment is sent	0.5
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	TD-347 -- iOS - Display Action Message in Chat	3.33
TD-284 -- Application is crashed when delete the message.	TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	1.12
Call With CometChat	TD-283 -- Showing Typing Indicator even when app is closed	3.33
Call With CometChat	TD-277 -- Chat Listing page should be refreshed.	0.75
TD-387--IOS: Notification delay	TD-285-- Loader moves continuously not stop	1.75
TD-282 -- Edit Chat message is not working properly	TD-346--Display Action Message in Chat	3.33
TD-339-- IOS : Received notification in the group chat	TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel	0.95
TD-386--Notification click redirection	TD-343--Android: Show the loader when attachment is sent	0.17
TD-349--User shows as online even when user is closed or logout	TD-240 -- iOS - Customization -- Reply to Chat Message	9.17
TD-280 -- User shows as online even when app is closed or in background	TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	4.92
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.	TD-234 -- iOS - Step #9-1 -- Send Notification	3.33
TD-281 -- Showing Typing Indicator even when app is closed	TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	12.58
TD-282 -- Edit Chat message is not working properly	TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat	3.25
TD-272 -- IOS app crashes when clicking on chat	TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members	3.75
TD-275 -- Chat page should be refreshed.	TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure	2.75
TD-340 -- IOS : Group chat scrolling is not working	TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion	4.75
TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message	TD-256 -- AND - Step #9-1 -- Send Notification	3.25
TD-349--User shows as online even when user is closed or logout	TD-262 -- AND - Customization -- Reply to Chat Message	9.25
TD-339-- IOS : Received notification in the group chat	TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	12.75
TD-276 -- Chat Listing page should be refreshed.	TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat	3.5
TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.	TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button	2.17
TD-286 -- Unable to Delete Message from Reply Thread	TD-289-- Remove the Tost message	0.67
TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button	TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat	4.25
TD-342--Show the loader when attachment is sent	TD-369--Message Input Loses Focus After Sending in Chat	1.25
TD-347 -- iOS - Display Action Message in Chat	TD-362--Three-Dot Menu Overlaps with Message Layout	2.17
TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	TD-273 -- Show the login and close button instead of ok	1.08
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages	TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	2.17
TD-283 -- Showing Typing Indicator even when app is closed	TD-354--Thread Replies Still Visible After Main Message Is Deleted	0.7
TD-277 -- Chat Listing page should be refreshed.	TD-360--New Message Not Sending After Editing a Previous Message	1.25
TD-285-- Loader moves continuously not stop	TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	2.25
TD-346--Display Action Message in Chat	TD-357--Add the attachment functionality inside the thread.	4.25
TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel	TD-356--Edit Option Should Not Appear for Image and Document	0.67
TD-343--Android: Show the loader when attachment is sent	TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	2.25
TD-284 -- Application is crashed when delete the message.	TD-352--Three-dot message menu does not close on outside click	1.17
TD-280 -- User shows as online even when app is closed or in background	TD-351--Increase Clickable Area for Document Download in Chat	0.67
TD-240 -- iOS - Customization -- Reply to Chat Message	TD-350--Set the Proper design	0.67
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion	TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	2.17
TD-234 -- iOS - Step #9-1 -- Send Notification	TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	14.5
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration	TD-218 -- Web - Customization -- Reply to Chat Message	13.75
TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat	TD-217 -- Web - Customization -- Edit Chat Message	4.58
TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members	TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page	1.25
TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure	TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	4.5
TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion	TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result	1.25
Call With CometChat	TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)	1.33
Call With CometChat	TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group	1.75
TD-256 -- AND - Step #9-1 -- Send Notification	TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens	3.25
TD-262 -- AND - Customization -- Reply to Chat Message	TD-210 -- Web - Step #5-3 -- Implement Typing Indicators	2.33
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration	TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	2.5
TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat	TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure	1.17
TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button	Crash App while open keyboard in Arena Chat	0.75
TD-289-- Remove the Tost message	SCRUM Meeting and Team Discussion	2.11
TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat	TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap	1.33
TD-369--Message Input Loses Focus After Sending in Chat	TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure	3.25
TD-362--Three-Dot Menu Overlaps with Message Layout	TD-186 -- Web - Step #4-2 -- Logout from CometChat	2
TD-273 -- Show the login and close button instead of ok	TD-185 -- Web - Step #4-1 -- Login to CometChat	1.92
TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members	3.8
TD-362--Three-Dot Menu Overlaps with Message Layout	TD-261 -- AND - Customization -- Edit Chat Message	7.5
TD-369--Message Input Loses Focus After Sending in Chat	TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure	2.47
TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group	TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat	3.33
TD-354--Thread Replies Still Visible After Main Message Is Deleted	TD-257 -- AND - Step #9-2 -- Do Not Send Notifications for Group Chat	0.25
TD-360--New Message Not Sending After Editing a Previous Message	TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	6.05
TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap	3.25
TD-357--Add the attachment functionality inside the thread.	TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure	2.58
TD-356--Edit Option Should Not Appear for Image and Document	TD-182 -- BE - Step #10 -- Notification Setup	3.5
TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	TD-179 -- BE - Step #7 -- API to Identify Whether a User is a Friend or Not	3.5
TD-352--Three-dot message menu does not close on outside click	TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure	2.92
TD-351--Increase Clickable Area for Document Download in Chat	TD-258 -- AND - Customization #2-1 -- Display Unread Message Count	3.08
TD-350--Set the Proper design	TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count	2.16
TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	TD-271 -- Display the same consistent message on iOS as shown on Android.	0.42
TD-342--Show the loader when attachment is sent	TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App	2.3
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing	TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App	2.33
TD-357--Add the attachment functionality inside the thread.	TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App	2.15
TD-218 -- Web - Customization -- Reply to Chat Message	TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App	2.08
TD-360--New Message Not Sending After Editing a Previous Message	TD-239 -- iOS - Customization -- Edit Chat Message	8
TD-217 -- Web - Customization -- Edit Chat Message	TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality	4.3
TD-359--Popup for Leave Group Confirmation Instead of Browser Alert	TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality	4.5
TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button	TD-250 -- AND - Step #5-4 -- Implement Typing Indicators	3
TD-350--Set the Proper design	TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators	3
TD-351--Increase Clickable Area for Document Download in Chat	TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature	3.85
TD-352--Three-dot message menu does not close on outside click	TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature	4.17
TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling	TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap	3.2
TD-354--Thread Replies Still Visible After Main Message Is Deleted	TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap	2.75
TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User	TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations	5.92
TD-356--Edit Option Should Not Appear for Image and Document	TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations	5.75
TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page	TD-181 -- BE - Step #9 -- Manage Flag for Disabling Chat	3
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)	TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat	4
TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result	TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players	8.5
TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)	TD-177 -- BE - Step #5 -- Register User in CometChat Upon Signup	3
TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group	TD-268 -- BE - Step #4A -- Sync All the old teams	5
TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens	TD-184 -- Web - Step #3-2 -- Initialize CometChat SDK	2
TD-210 -- Web - Step #5-3 -- Implement Typing Indicators	TD-183 -- Web - Step #3-1 -- Integrate CometChat SDK	2
TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature	TD-176 -- BE - Step #4 -- Sync All Old App Users	5.5
TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure	TD-175 -- BE - Step #3 -- Integrate CometChat SDK	1.5
TD-346--Display Action Message in Chat	TD-242 -- AND - Step #3-2 -- Initialize CometChat SDK	2
TD-347 -- iOS - Display Action Message in Chat	TD-220 -- iOS - Step #3-2 -- Initialize CometChat SDK	2
Crash App while open keyboard in Arena Chat	TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)	2.5
SCRUM Meeting and Team Discussion	TD-219 -- iOS - Step #3-1 -- Integrate CometChat SDK	2.83
TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap	Check and Update Sprint 5 Task Estimate	2.5
TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure	Working on Action Item & Update Task/Story	1.75
TD-186 -- Web - Step #4-2 -- Logout from CometChat	Jira – Confluence Page and Task Create	9.75
TD-185 -- Web - Step #4-1 -- Login to CometChat		0
TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members		0
TD-285-- Loader moves continuously not stop		0
TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel		0
TD-261 -- AND - Customization -- Edit Chat Message		0
TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure		0
TD-340 -- IOS : Group chat scrolling is not working		0
TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat		0
TD-257 -- AND - Step #9-2 -- Do Not Send Notifications for Group Chat		0
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap		0
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap		0
TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure		0
TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages		0
TD-182 -- BE - Step #10 -- Notification Setup		0
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages		0
TD-179 -- BE - Step #7 -- API to Identify Whether a User is a Friend or Not		0
TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure		0
TD-258 -- AND - Customization #2-1 -- Display Unread Message Count		0
TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count		0
SCRUM Meeting and Team Discussion		0
TD-271 -- Display the same consistent message on iOS as shown on Android.		0
TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button		0
TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message		0
TD-286 -- Unable to Delete Message from Reply Thread		0
TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button		0
TD-289-- Remove the Tost message		0
TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App		0
TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App		0
TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App		0
TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App		0
TD-282 -- Edit Chat message is not working properly		0
TD-281 -- Showing Typing Indicator even when app is closed		0
TD-271 -- Display the same consistent message on iOS as shown on Android.		0
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.		0
TD-283 -- Showing Typing Indicator even when app is closed		0
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)		0
TD-239 -- iOS - Customization -- Edit Chat Message		0
TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality		0
TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality		0
TD-250 -- AND - Step #5-4 -- Implement Typing Indicators		0
TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators		0
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.		0
TD-276 -- Chat Listing page should be refreshed.		0
TD-275 -- Chat page should be refreshed.		0
TD-272 -- IOS app crashes when clicking on chat		0
TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.		0
TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page		0
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)		0
TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result		0
TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)		0
TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens		0
TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat		0
TD-277 -- Chat Listing page should be refreshed.		0
TD-273 -- Show the login and close button instead of ok		0
TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature		0
TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature		0
TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap		0
TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap		0
TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations		0
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
TD-262 -- AND - Customization -- Reply to Chat Message		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
TD-218 -- Web - Customization -- Reply to Chat Message		0
SCRUM Meeting and Team Discussion		0
TD-262 -- AND - Customization -- Reply to Chat Message		0
TD-261 -- AND - Customization -- Edit Chat Message		0
TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat		0
TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature		0
TD-210 -- Web - Step #5-3 -- Implement Typing Indicators		0
TD-217 -- Web - Customization -- Edit Chat Message		0
TD-261 -- AND - Customization -- Edit Chat Message		0
TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion		0
TD-240 -- iOS - Customization -- Reply to Chat Message		0
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing		0
TD-258 -- AND - Customization #2-1 -- Display Unread Message Count		0
TD-256 -- AND - Step #9-1 -- Send Notification		0
TD-239 -- iOS - Customization -- Edit Chat Message		0
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion		0
TD-181 -- BE - Step #9 -- Manage Flag for Disabling Chat		0
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion		0
TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count		0
TD-234 -- iOS - Step #9-1 -- Send Notification		0
TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat		0
TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat		0
TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality		0
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration		0
TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality		0
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration		0
TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group		0
TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap		0
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration		0
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration		0
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing		0
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing		0
TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players		0
TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat		0
TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members		0
TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat		0
TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members		0
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap		0
TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players		0
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing		0
TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure		0
TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure		0
TD-177 -- BE - Step #5 -- Register User in CometChat Upon Signup		0
TD-268 -- BE - Step #4A -- Sync All the old teams		0
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap		0
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap		0
TD-250 -- AND - Step #5-4 -- Implement Typing Indicators		0
TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature		0
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap		0
TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators		0
TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature		0
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations		0
TD-186 -- Web - Step #4-2 -- Logout from CometChat		0
TD-185 -- Web - Step #4-1 -- Login to CometChat		0
TD-184 -- Web - Step #3-2 -- Initialize CometChat SDK		0
TD-183 -- Web - Step #3-1 -- Integrate CometChat SDK		0
TD-268 -- BE - Step #4A -- Sync All the old teams		0
TD-176 -- BE - Step #4 -- Sync All Old App Users		0
TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations		0
TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap		0
TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure		0
TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App		0
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations		0
SCRUM Meeting and Team Discussion		0
TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap		0
TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure		0
TD-176 -- BE - Step #4 -- Sync All Old App Users		0
TD-175 -- BE - Step #3 -- Integrate CometChat SDK		0
TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure		0
TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App		0
TD-242 -- AND - Step #3-2 -- Initialize CometChat SDK		0
TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure		0
TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App		0
TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App		0
TD-220 -- iOS - Step #3-2 -- Initialize CometChat SDK		0
TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)		0
TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)		0
TD-219 -- iOS - Step #3-1 -- Integrate CometChat SDK		0
SCRUM Meeting and Team Discussion		0
Check and Update Sprint 5 Task Estimate		0
Working on Action Item & Update Task/Story		0
Jira – Confluence Page and Task Create		0
Jira – Confluence Page and Task Create		0

## Overview
Type	Item	Link	Estimation	Development Hours	QA Hours	PM Hours
Story	TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-124	6	5.33	0.75				Person Name	Hours Spent
Story	TD - 125 -- AND - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-125	6	8	0.75				Jayesh Rathod	2.4
Story	TD - 126 -- BE - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-126	8	5.75	0.42				Kishan Dharajiya	15.75
Story	TD - 128 -- IOS - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-128	0.5	1.92	0.34				Usama Shaikh	7
Story	TD - 129 -- AND - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-129	0.5	0.42	0.17				Pranay Prajapati	13.25
Story	TD - 132 -- BE - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-132	12	9.5	0.25				HasanAli	11.92
Story	TD - 133 -- WEB - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-133	8	7	1.17				Dhruvin Soni	12.43
Story	TD - 134 -- BE - Manual Cron Run for DST Timezone Issue	https://tussly.atlassian.net/browse/TD-134	0.5	0.5	0.25				Total	62.75
Bug	TD - 136 -- AND - Player Card Loading Issue for Non-Tournament Users on Android	https://tussly.atlassian.net/browse/TD-135	3.5	2.5	0.5
	Test tournament leaderboard with different browser and devices			0	4
	Test Push notification after upgrade push notification system			0	2.5
	Test replace home screen image in application			0	1
	Client Call and Demo Sprint 3			2	0.33
	Testing stage statistics leaderboard			5	0
Total			45	47.92	12.43	2.4

## Logs
Type	Item	Link	Notes	Hours	Person	Date
	Test tournament leaderboard with different browser and devices	https://tussly.atlassian.net/browse/TD-167	Checking tournament all leader board, player , character ad stage. By playing tournament, update by organizer, forfeit match, manual update and etc...	4	Dhruvin Soni	2025-03-03
	Test Push notification after upgrade push notification system	https://tussly.atlassian.net/browse/TD-165	Testing Notification. Play Tournament to test all notification for tournament check in, check in closing soon, match scheduled etc...	2.5	Dhruvin Soni	2025-02-28
	Test replace home screen image in application	https://tussly.atlassian.net/browse/TD-166	Test replace home screen image. Conduct Compatibility Testing Across Devices, Android devices and latest versions of OS and teat in lemdatest. Same way test iOS devices with different devices and in lemdateast.	1	Dhruvin Soni	2025-02-28
	Client Call and Demo Sprint 3		Sprint 3 Retrospective Meeting	0.67	HasanAli	2025-01-20
	Client Call and Demo Sprint 3		Sprint 3 Retrospective Meeting	0.67	Pranay Prajapati	2025-01-20
Story	TD - 128 -- IOS - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-128	Update screen design to make pre login and post login screen visible same. Create build and upload to TestFlight.	1.5	Pranay Prajapati	2025-01-16
Story	TD - 128 -- IOS - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-128	--> The task has been successfully completed. I have reviewed the issue and found that it occurred due to two different designs being implemented for the Home and Initial screens. This issue can be resolved.	0.17	Dhruvin Soni	2025-01-16
Bug	TD - 136 -- AND - Player Card Loading Issue for Non-Tournament Users on Android	https://tussly.atlassian.net/browse/TD-136	Finding the Exact Scenario of Issue. Manage When New User Or Data Not Found that time hide Loader and Manage UI.	2.5	HasanAli	2025-01-13
Bug	TD - 136 -- AND - Player Card Loading Issue for Non-Tournament Users on Android	https://tussly.atlassian.net/browse/TD-136	The Issue has been completed. The issue with player reports during new user registration has been resolved. Additionally, the loader now functions correctly, and the app no longer restarts unexpectedly.	0.5	Dhruvin Soni	2025-01-13
Story	TD - 133 -- WEB - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-133	--> Retest the task.	0.17	Dhruvin Soni	2025-01-13
	Client Call and Demo Sprint 3		Call with client, about sprint 3 demo, and task review.	0.33	Dhruvin Soni	2025-01-08
	Client Call and Demo Sprint 3		Call with client, about sprint 3 demo, and task review.	0.33	HasanAli	2025-01-08
	Client Call and Demo Sprint 3		Call with client, about sprint 3 demo, and task review.	0.33	Pranay Prajapati	2025-01-08
Story	TD - 128 -- IOS - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-128	--> Retest the task	0.17	Dhruvin Soni	2025-01-08
Story	TD - 128 -- IOS - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-128	Replace the current home screen image with the designated new image file, home screen loads without any performance degradation. The new image is responsive and displays correctly across all devices.	0.42	Pranay Prajapati	2025-01-08
Story	TD - 129 -- AND - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-129	--> Retest the task.	0.17	Dhruvin Soni	2025-01-08
Story	TD - 129 -- AND - Replace Home Screen image	https://tussly.atlassian.net/browse/TD-129	Replace the current home screen image with the designated new image file, home screen loads without any performance degradation. The new image is responsive and displays correctly across all devices.	0.42	HasanAli	2025-01-07
	Client Call		Client Call	0.4	Jayesh Rathod	2025-01-07
Story	TD - 132 -- BE - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-132	debug the issue solve the stage count issue	3	Kishan Dharajiya	2025-01-03
Story	TD - 134 -- BE - Manual Cron Run for DST Timezone Issue	https://tussly.atlassian.net/browse/TD-134	--> The task has been completed. I have verified the current time based on the selected time zone, and you can update the time zone if needed.	0.25	Dhruvin Soni	2025-01-03
Story	TD - 126 -- BE - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-126	--> Retest the issue. Test the push notification and verify whether the redirection is functioning correctly.	0.17	Dhruvin Soni	2025-01-03
Story	TD - 125 -- AND - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-125	--> Retest the push notification. Test the push notification and verify whether the redirection is functioning correctly.	0.25	Dhruvin Soni	2025-01-03
Story	TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-124	--> Retest the push notification. Test the push notification and verify whether the redirection is functioning correctly.	0.25	Dhruvin Soni	2025-01-03
Story	TD - 126 -- BE - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-126	--> Testing the push notification. Find the issue and assign to the developers.	0.25	Dhruvin Soni	2025-01-03
Story	TD - 132 -- BE - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-132	--> Testing the task. Play 2 tournament and check the stage statistics and compare all the data.	0.25	Dhruvin Soni	2025-01-03
Story	TD - 133 -- WEB - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-133	--> Testing the task. Play 2 tournament and check the stage statistics and compare all the data.	1	Dhruvin Soni	2025-01-03
Story	TD - 126 -- BE - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-126	Check the notification not work some time, The FCM token was invalid that why notification not fire	3.25	Kishan Dharajiya	2025-01-03
Story	TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-124	--> Testing the push notification. Find the issue and assign to the developers.	0.5	Dhruvin Soni	2025-01-03
Story	TD - 125 -- AND - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-125	--> Testing the push notification. Find the issue and assign to the developers.	0.5	Dhruvin Soni	2025-01-03
	Preparing Sprint & Client Discussion		Prepare sprint and estimation for sprint 3 with following tasks Upgrade push notifications, DST timezone, Home page screen replace Discussion with alex and team to update the format	1.5	Jayesh Rathod	2025-01-03
	Testing stage statistics leaderboard		Check stage leader board. Get one issue in stage leader board, count of pick stage is double then selected.	5	Pranay Prajapati	2025-01-03
Story	TD - 125 -- AND - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-125	I'm checking whether notifications arrive or not. After updating Android Studio, I get an issue with notifications. I get an issue with notifications received due to a syntax and method change. I updated the syntax and changed some syntax and keywords to get notifications received after firing notifications from the backend.	4	HasanAli	2025-01-02
Story	TD - 133 -- WEB - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-133	Added Sorting with API Implementation	4	Usama Shaikh	2025-01-02
Story	TD - 126 -- BE - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-126	Solve the notification custom payload data and action_click for android & IOS	2.5	Kishan Dharajiya	2025-01-02
Story	TD - 132 -- BE - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-132	Create API for get the stage ban & pick stage leader board, Add sorting functionality for sort stage, default sorting stage pick,	6.5	Kishan Dharajiya	2025-01-02
Story	TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-124	I'm checking whether notifications arrive or not. After updating Xcode, I get an issue with notifications. I get an issue with notifications received due to a syntax and method change. I updated the syntax and changed some syntax and keywords to get notifications received after firing notifications from the backend.	5.33	Pranay Prajapati	2025-01-02
Story	TD - 125 -- AND - Upgrade Push Notification System to Latest APIs	https://tussly.atlassian.net/browse/TD-125	Update Firebase Notification Library and solve version Issue.	4	HasanAli	2024-12-31
Story	TD - 133 -- WEB - Stage Statistics Leaderboard	https://tussly.atlassian.net/browse/TD-133	Create Leaderboard Design	3	Usama Shaikh	2024-12-31
Story	TD - 134 -- BE - Manual Cron Run for DST Timezone Issue	https://tussly.atlassian.net/browse/TD-134	Excute timezone API manually on UAT server and check the timezone data on database	0.5	Kishan Dharajiya	2024-12-30
	SCRUM Meeting and Team Discussion		Sprint meeting with team and sprint 3 discussion	0.5	Jayesh Rathod	2024-12-26

## Sheet7
A
B
C
D
E
F
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
V
W
X
Y
Z

## Sheet8
D	1	D
T		0
V	1	V
A	1	A
N		0
H	1	H
U		0
Z	1	Z
	5	5

## 'file:///Users/auxano/Documents/untitled%20folder/SwiftUI/SwiftUI-Demo/Sheet%20Calc/GetUniqueValues.xls'#Sprint 5 Log
Item			Hours	Person
Call With CometChat			1	Jayesh Rathod
Call With CometChat			1	Pranay Prajapati
TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync			0.5	Kinjal Shah
TD-410 -- Dismiss Keyboard on Outside Tap			3	Pranay Prajapati
TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players			0.33	Kinjal Shah
TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section			0.25	Kinjal Shah
TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support			0.25	Kinjal Shah
TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt			0.33	Kinjal Shah
TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat			0.17	Kinjal Shah
TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon			0.25	Kinjal Shah
TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging			0.25	Kinjal Shah
TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync			0.17	Kinjal Shah
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon			0.17	Kinjal Shah
TD-413 -- Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging			2.25	Pranay Prajapati
TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read			0.17	Kinjal Shah
TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)			0.25	Kinjal Shah
TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat			0.17	Kinjal Shah
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon			0.25	Kinjal Shah
TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging			0.25	Kinjal Shah
TD-417 -- iOS Crash in Arena During Chat Usage, Followed by Arena State Desync			2.67	Pranay Prajapati
TD-419 -- iOS Users Unable to Call Organizer into Arena Chat – Error Triggered on Attempt			3	Pranay Prajapati
TD-420 -- iOS Users Do Not Receive First Message from Organizer in Arena Chat			2	Pranay Prajapati
TD-412 -- User Receives Second Notification When Message is Deleted Before Being Read			0.17	Pranay Prajapati
TD-414 -- Unnecessary Second Push Notification Triggered by Message Edits (Related to TD-412)			0.17	Pranay Prajapati
TD-425 -- AND - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync			2	HasanAli
TD-426 -- AND - Main Chat Icon Does Not Update with Unread Count on App Resume After Background Messaging			0.75	HasanAli
TD-423 -- AND - Unread Message Counter Missing on Arena Chat Icon			1	HasanAli
TD-427 -- AND - Add Confirmation Pop-Up Before Adding Admin to Arena Chat			1	HasanAli
TD-411 -- iOS - Chat History and Real-Time Events Not Loading on First Login – Requires Logout/Login to Sync			3	Pranay Prajapati
TD-416 -- iOS - Unread Message Counter Missing on Arena Chat Icon			4	Pranay Prajapati
TD-424 -- iOS - Add Confirmation Pop-Up Before Adding Admin to Arena Chat			1	Pranay Prajapati
TD-418 -- Add Back Button to Chat Page for Organizers to Return to Previous Panel Section			1	Usama Shaikh
TD-415 -- Organizer Chat Icon Fails to Create Group Chat with Checked-In Players			2	Usama Shaikh
TD-421 -- Organizer Unable to Leave Group Chat in Arena Match Support			2	Usama Shaikh
TD-428 -- AND - App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging			5	HasanAli
TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging			5	Pranay Prajapati
TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)			4	Pranay Prajapati
TD-409 -- App Crashes When Viewing Chatroom and New Friend Starts Typing or Messaging			3	Pranay Prajapati
TD-408 -- iOS App Crash with Orange Microphone Indicator After Initial Use (Likely SDK-Triggered Audio Session)			4.5	Pranay Prajapati
TD-405 -- Web - Enable or Implement “Invite via Link” Functionality on Team Page			1	Usama Shaikh
TD-386--Notification click redirection			0.25	Kinjal Shah
TD-385--Notification click redirection			0.25	Kinjal Shah
TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages			0.17	Kinjal Shah
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages			0.17	Kinjal Shah
TD-284 -- Application is crashed when delete the message.			0.17	Kinjal Shah
Call With CometChat			1	Jayesh Rathod
Call With CometChat			1	Pranay Prajapati
TD-387--IOS: Notification delay			1.5	Pranay Prajapati
TD-282 -- Edit Chat message is not working properly			0.17	Kinjal Shah
TD-339-- IOS : Received notification in the group chat			0.33	Pranay Prajapati
TD-386--Notification click redirection			1.5	Pranay Prajapati
TD-349--User shows as online even when user is closed or logout			0.17	Kinjal Shah
TD-280 -- User shows as online even when app is closed or in background			0.33	Kinjal Shah
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.			0.33	Kinjal Shah
TD-281 -- Showing Typing Indicator even when app is closed			0.17	Kinjal Shah
TD-282 -- Edit Chat message is not working properly			0.25	Kinjal Shah
TD-272 -- IOS app crashes when clicking on chat			0.17	Kinjal Shah
TD-275 -- Chat page should be refreshed.			0.17	Kinjal Shah
TD-340 -- IOS : Group chat scrolling is not working			0.17	Kinjal Shah
TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message			0.25	Kinjal Shah
TD-349--User shows as online even when user is closed or logout			1	Usama Shaikh
TD-339-- IOS : Received notification in the group chat			0.17	Kinjal Shah
TD-276 -- Chat Listing page should be refreshed.			0.17	Kinjal Shah
TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.			0.08	Kinjal Shah
TD-286 -- Unable to Delete Message from Reply Thread			0.2	Kinjal Shah
TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button			0.17	Kinjal Shah
TD-342--Show the loader when attachment is sent			0.17	Kinjal Shah
TD-347 -- iOS - Display Action Message in Chat			0.33	Kinjal Shah
TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling			0.12	Kinjal Shah
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages			0.25	Kinjal Shah
TD-283 -- Showing Typing Indicator even when app is closed			0.33	Kinjal Shah
TD-277 -- Chat Listing page should be refreshed.			0.25	Kinjal Shah
TD-285-- Loader moves continuously not stop			0.25	Kinjal Shah
TD-346--Display Action Message in Chat			0.33	Kinjal Shah
TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel			0.2	Kinjal Shah
TD-343--Android: Show the loader when attachment is sent			0.17	Kinjal Shah
TD-284 -- Application is crashed when delete the message.			0.17	Pranay Prajapati
TD-280 -- User shows as online even when app is closed or in background			0.17	Pranay Prajapati
TD-240 -- iOS - Customization -- Reply to Chat Message			1.17	Kinjal Shah
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion			0.42	Kinjal Shah
TD-234 -- iOS - Step #9-1 -- Send Notification			0.58	Kinjal Shah
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration			0.58	Kinjal Shah
TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat			0.5	Kinjal Shah
TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members			0.5	Kinjal Shah
TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure			0.25	Kinjal Shah
TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion			0.5	Kinjal Shah
Call With CometChat			1	Jayesh Rathod
Call With CometChat			1	Pranay Prajapati
TD-256 -- AND - Step #9-1 -- Send Notification			0.75	Kinjal Shah
TD-262 -- AND - Customization -- Reply to Chat Message			1.25	Kinjal Shah
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration			0.75	Kinjal Shah
TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat			0.5	Kinjal Shah
TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button			0.17	Kinjal Shah
TD-289-- Remove the Tost message			0.17	Kinjal Shah
TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat			0.25	Kinjal Shah
TD-369--Message Input Loses Focus After Sending in Chat			0.25	Kinjal Shah
TD-362--Three-Dot Menu Overlaps with Message Layout			0.17	Kinjal Shah
TD-273 -- Show the login and close button instead of ok			0.08	Kinjal Shah
TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group			0.17	Kinjal Shah
TD-362--Three-Dot Menu Overlaps with Message Layout			2	Usama Shaikh
TD-369--Message Input Loses Focus After Sending in Chat			1	Usama Shaikh
TD-373--Left-Side Chat List Not Updated Immediately After Leaving Group			2	Usama Shaikh
TD-354--Thread Replies Still Visible After Main Message Is Deleted			0.2	Kinjal Shah
TD-360--New Message Not Sending After Editing a Previous Message			0.25	Kinjal Shah
TD-359--Popup for Leave Group Confirmation Instead of Browser Alert			0.25	Kinjal Shah
TD-357--Add the attachment functionality inside the thread.			0.25	Kinjal Shah
TD-356--Edit Option Should Not Appear for Image and Document			0.17	Kinjal Shah
TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User			0.25	Kinjal Shah
TD-352--Three-dot message menu does not close on outside click			0.17	Kinjal Shah
TD-351--Increase Clickable Area for Document Download in Chat			0.17	Kinjal Shah
TD-350--Set the Proper design			0.17	Kinjal Shah
TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button			0.17	Kinjal Shah
TD-342--Show the loader when attachment is sent			0.33	Pranay Prajapati
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing			1	Kinjal Shah
TD-357--Add the attachment functionality inside the thread.			4	Usama Shaikh
TD-218 -- Web - Customization -- Reply to Chat Message			0.75	Kinjal Shah
TD-360--New Message Not Sending After Editing a Previous Message			1	Usama Shaikh
TD-217 -- Web - Customization -- Edit Chat Message			0.58	Kinjal Shah
TD-359--Popup for Leave Group Confirmation Instead of Browser Alert			2	Usama Shaikh
TD-348--Duplicate Messages Sent on Multiple Quick Taps of Send Button			2	Usama Shaikh
TD-350--Set the Proper design			0.5	Usama Shaikh
TD-351--Increase Clickable Area for Document Download in Chat			0.5	Usama Shaikh
TD-352--Three-dot message menu does not close on outside click			1	Usama Shaikh
TD-353--Three-Dot Menu on Last Message Not Fully Visible Without Scrolling			1	Usama Shaikh
TD-354--Thread Replies Still Visible After Main Message Is Deleted			0.5	Usama Shaikh
TD-355--Thread Messages Not Updating in Real-Time After Edit or Delete by Other User			2	Usama Shaikh
TD-356--Edit Option Should Not Appear for Image and Document			0.5	Usama Shaikh
TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page			0.25	Kinjal Shah
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)			0.5	Kinjal Shah
TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result			0.25	Kinjal Shah
TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)			0.33	Kinjal Shah
TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group			0.25	Kinjal Shah
TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens			0.25	Kinjal Shah
TD-210 -- Web - Step #5-3 -- Implement Typing Indicators			0.33	Kinjal Shah
TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature			0.5	Kinjal Shah
TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure			0.17	Kinjal Shah
TD-346--Display Action Message in Chat			3	HasanAli
TD-347 -- iOS - Display Action Message in Chat			3	Pranay Prajapati
Crash App while open keyboard in Arena Chat			0.75	Pranay Prajapati
SCRUM Meeting and Team Discussion			0.33	Jayesh Rathod
TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap			0.33	Kinjal Shah
TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure			0.25	Kinjal Shah
TD-186 -- Web - Step #4-2 -- Logout from CometChat			0.5	Kinjal Shah
TD-185 -- Web - Step #4-1 -- Login to CometChat			0.42	Kinjal Shah
TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members			0.5	Kinjal Shah
TD-285-- Loader moves continuously not stop			1.5	HasanAli
TD -341--Edited Message Not Cleared from Input Field After Clicking Cancel			0.75	HasanAli
TD-261 -- AND - Customization -- Edit Chat Message			0.5	Kinjal Shah
TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure			0.17	Kinjal Shah
TD-340 -- IOS : Group chat scrolling is not working			3.5	Pranay Prajapati
TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat			0.33	Kinjal Shah
TD-257 -- AND - Step #9-2 -- Do Not Send Notifications for Group Chat			0.25	Kinjal Shah
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap			0.25	Kinjal Shah
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap			0.25	Kinjal Shah
TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure			0.25	Kinjal Shah
TD-294-- IOS : Unread Count Still Visible After Reading Chat Messages			0.75	Pranay Prajapati
TD-182 -- BE - Step #10 -- Notification Setup			3.5	Kishan Dharajiya
TD -- 293 Android : Unread Count Still Visible After Reading Chat Messages			1.5	HasanAli
TD-179 -- BE - Step #7 -- API to Identify Whether a User is a Friend or Not			3.5	Kishan Dharajiya
TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure			0.42	Kinjal Shah
TD-258 -- AND - Customization #2-1 -- Display Unread Message Count			0.58	Kinjal Shah
TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count			0.33	Kinjal Shah
SCRUM Meeting and Team Discussion			0.5	Jayesh Rathod
TD-271 -- Display the same consistent message on iOS as shown on Android.			0.17	Kinjal Shah
TD --291 Duplicate Messages Sent on Multiple Quick Taps of Send Button			1.33	Pranay Prajapati
TD-290 -- Chat Does Not Auto-Scroll down to see Latest Message			2.25	Pranay Prajapati
TD-286 -- Unable to Delete Message from Reply Thread			0.75	Pranay Prajapati
TD--292 Duplicate Messages Sent on Multiple Quick Taps of Send Button			2	HasanAli
TD-289-- Remove the Tost message			0.5	HasanAli
TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App			0.5	Kinjal Shah
TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App			0.5	Kinjal Shah
TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App			0.25	Kinjal Shah
TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App			0.25	Kinjal Shah
TD-282 -- Edit Chat message is not working properly			4	Pranay Prajapati
TD-281 -- Showing Typing Indicator even when app is closed			0.5	Pranay Prajapati
TD-271 -- Display the same consistent message on iOS as shown on Android.			0.25	Pranay Prajapati
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.			2	Pranay Prajapati
TD-283 -- Showing Typing Indicator even when app is closed			3	HasanAli
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)			2	Usama Shaikh
TD-239 -- iOS - Customization -- Edit Chat Message			1	Kinjal Shah
TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality			0.5	Kinjal Shah
TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality			0.5	Kinjal Shah
TD-250 -- AND - Step #5-4 -- Implement Typing Indicators			1	Kinjal Shah
TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators			1	Kinjal Shah
TD-278 -- The message appears as "read" even though it hasn't actually been read by the recipient.			1	Pranay Prajapati
TD-276 -- Chat Listing page should be refreshed.			0.83	Pranay Prajapati
TD-275 -- Chat page should be refreshed.			0.75	Pranay Prajapati
TD-272 -- IOS app crashes when clicking on chat			2	Pranay Prajapati
TD-270 --Show a pop-up on iOS when chat is tapped by a user who is not logged in or registered.			0.25	Pranay Prajapati
TD-216 -- Web - Customization #5-4 -- Chat from Player Details Page			1	Usama Shaikh
TD-215 -- Web - Customization #5-3 -- Chat from Player List (Teams & Player)			2	Usama Shaikh
TD-214 -- Web - Customization #5-2 -- Chat from Scoreboard & Result			1	Usama Shaikh
TD-213 -- Web - Customization #5-1 -- Chat from Scheduled Subsection (Scheduled & Bracket)			1	Usama Shaikh
TD-211 -- Web - Step #6-1 -- Group Chat on Chat Icon Tap in Scheduled & Scoreboards Screens			3	Usama Shaikh
TD-279 -- Chat History Not Visible When Scrolling Up in Player Chat			4	HasanAli
TD-277 -- Chat Listing page should be refreshed.			0.5	HasanAli
TD-273 -- Show the login and close button instead of ok			1	HasanAli
TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature			1.5	Kinjal Shah
TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature			1.67	Kinjal Shah
TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap			0.5	Kinjal Shah
TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap			0.25	Kinjal Shah
TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations			0.42	Kinjal Shah
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations			0.25	Kinjal Shah
TD-218 -- Web - Customization -- Reply to Chat Message			2	Usama Shaikh
TD-218 -- Web - Customization -- Reply to Chat Message			1.5	Usama Shaikh
TD-218 -- Web - Customization -- Reply to Chat Message			1.5	Usama Shaikh
TD-262 -- AND - Customization -- Reply to Chat Message			3	HasanAli
TD-218 -- Web - Customization -- Reply to Chat Message			2	Usama Shaikh
TD-218 -- Web - Customization -- Reply to Chat Message			3	Usama Shaikh
TD-218 -- Web - Customization -- Reply to Chat Message			2	Usama Shaikh
TD-218 -- Web - Customization -- Reply to Chat Message			1	Usama Shaikh
SCRUM Meeting and Team Discussion			0.45	Jayesh Rathod
TD-262 -- AND - Customization -- Reply to Chat Message			5	HasanAli
TD-261 -- AND - Customization -- Edit Chat Message			3	HasanAli
TD-235 -- iOS - Step #9-2 -- Do Not Send Notifications for Group Chat			3	Pranay Prajapati
TD-207 -- Web - Step #5-2 -- Implement Read Receipt Feature			2	Usama Shaikh
TD-210 -- Web - Step #5-3 -- Implement Typing Indicators			2	Usama Shaikh
TD-217 -- Web - Customization -- Edit Chat Message			4	Usama Shaikh
TD-261 -- AND - Customization -- Edit Chat Message			4	HasanAli
TD-260 -- AND - Customization #4-1 -- Disable Chat After Match Completion			4.25	HasanAli
TD-240 -- iOS - Customization -- Reply to Chat Message			8	Pranay Prajapati
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing			5	Usama Shaikh
TD-258 -- AND - Customization #2-1 -- Display Unread Message Count			2.5	HasanAli
TD-256 -- AND - Step #9-1 -- Send Notification			2.5	HasanAli
TD-239 -- iOS - Customization -- Edit Chat Message			7	Pranay Prajapati
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion			1	Pranay Prajapati
TD-181 -- BE - Step #9 -- Manage Flag for Disabling Chat			3	Kishan Dharajiya
TD-238 -- iOS - Customization #4-1 -- Disable Chat After Match Completion			3.5	Pranay Prajapati
TD-236 -- iOS - Customization #2-1 -- Display Unread Message Count			1.83	Pranay Prajapati
TD-234 -- iOS - Step #9-1 -- Send Notification			2.75	Pranay Prajapati
TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat			2	Kishan Dharajiya
TD-180 -- BE - Step #8 -- Admin Added to Arena Group Chat			2	Kishan Dharajiya
TD-255 -- AND - Step #7-1 -- Delete Chat Message Functionality			3.8	HasanAli
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration			4	HasanAli
TD-233 -- iOS - Step #7-1 -- Delete Chat Message Functionality			4	Pranay Prajapati
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration			4	Pranay Prajapati
TD-212 -- Web - Step #6-2 -- Admin Can Leave Arena Chat Group			1.5	Usama Shaikh
TD-207 -- Web - Step #5-1 -- Open Chat on Chat Icon Tap			1	Usama Shaikh
TD-254 -- AND - Step #6-4 -- Arena Player to Player Chat Integration			8	HasanAli
TD-232 -- iOS - Step #6-4 -- Arena Player to Player Chat Integration			8	Pranay Prajapati
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing			3	Usama Shaikh
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing			3	Usama Shaikh
TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players			4	Kishan Dharajiya
TD-253 -- AND - Step #6-3 -- Tournament Admin to Player Chat			3	HasanAli
TD-252 -- AND - Step #6-2 -- Implement Team Chat, Restrict to Team Members			3.3	HasanAli
TD-231 -- iOS - Step #6-3 -- Tournament Admin to Player Chat			2.75	Pranay Prajapati
TD-230 -- iOS - Step #6-2 -- Implement Team Chat, Restrict to Team Members			3.25	Pranay Prajapati
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap			2	Pranay Prajapati
TD-178 -- BE - Step #6 -- Create Group or One-to-One Chat Between Players			4.5	Kishan Dharajiya
TD-269 -- Web - Step #7 -- Web Chat Interface with Full Chat Listing			2.5	Usama Shaikh
TD-206 -- Web - Step #4-4 -- Handle CometChat Logout Failure			1	Usama Shaikh
TD-205 -- Web - Step #4-3 -- Handle CometChat Login Failure			3	Usama Shaikh
TD-177 -- BE - Step #5 -- Register User in CometChat Upon Signup			3	Kishan Dharajiya
TD-268 -- BE - Step #4A -- Sync All the old teams			2	Kishan Dharajiya
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap			3	HasanAli
TD-251 -- AND - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap			2.8	HasanAli
TD-250 -- AND - Step #5-4 -- Implement Typing Indicators			2	HasanAli
TD-249 -- AND - Step #5-3 -- Implement Read Receipt Feature			2.35	HasanAli
TD-229 -- iOS - Step #6-1 -- Navigate to Group Chat on Chat Icon Tap			1	Pranay Prajapati
TD-228 -- iOS - Step #5-4 -- Implement Typing Indicators			2	Pranay Prajapati
TD-227 -- iOS - Step #5-3 -- Implement Read Receipt Feature			2.5	Pranay Prajapati
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations			2.5	Pranay Prajapati
TD-186 -- Web - Step #4-2 -- Logout from CometChat			1.5	Usama Shaikh
TD-185 -- Web - Step #4-1 -- Login to CometChat			1.5	Usama Shaikh
TD-184 -- Web - Step #3-2 -- Initialize CometChat SDK			2	Usama Shaikh
TD-183 -- Web - Step #3-1 -- Integrate CometChat SDK			2	Usama Shaikh
TD-268 -- BE - Step #4A -- Sync All the old teams			3	Kishan Dharajiya
TD-176 -- BE - Step #4 -- Sync All Old App Users			3.5	Kishan Dharajiya
TD-248 -- AND - Step #5-2 -- Allow Users to View Past Conversations			5.5	HasanAli
TD-247 -- AND - Step #5-1 -- Navigate to Chat Message Screen on Chat Icon Tap			2.7	HasanAli
TD-246 -- AND - Step #4-4 -- Handle CometChat Logout Failure			2.3	HasanAli
TD-243 -- AND - Step #4-1 -- Log in to CometChat after User Authentication in the Android App			1.9	HasanAli
TD-226 -- iOS - Step #5-2 -- Allow Users to View Past Conversations			3	Pranay Prajapati
SCRUM Meeting and Team Discussion			0.5	Jayesh Rathod
TD-225 -- iOS - Step #5-1 -- Navigate to Chat Screen on Chat Icon Tap			2.5	Pranay Prajapati
TD-224 -- iOS - Step #4-4 -- Handle CometChat Logout Failure			2.5	Pranay Prajapati
TD-176 -- BE - Step #4 -- Sync All Old App Users			2	Kishan Dharajiya
TD-175 -- BE - Step #3 -- Integrate CometChat SDK			1.5	Kishan Dharajiya
TD-245 -- AND - Step #4-3 -- Handle CometChat Login Failure			2.5	HasanAli
TD-244 -- AND - Step #4-2 -- Log Out User from CometChat When Logging Out of the App			1.8	HasanAli
TD-242 -- AND - Step #3-2 -- Initialize CometChat SDK			2	HasanAli
TD-223 -- iOS - Step #4-3 -- Handle CometChat Login Failure			2.33	Pranay Prajapati
TD-222 -- iOS - Step #4-2 -- Log Out from CometChat When User Logs Out from the iOS App			1.83	Pranay Prajapati
TD-221 -- iOS - Step #4-1 -- Implement CometChat Login after User Authentication in iOS App			1.83	Pranay Prajapati
TD-220 -- iOS - Step #3-2 -- Initialize CometChat SDK			2	Pranay Prajapati
TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)			1	Kishan Dharajiya
TD-174 -- BE - Step #2 – Create an App in CometChat (Backend Setup)			1.5	Kishan Dharajiya
TD-219 -- iOS - Step #3-1 -- Integrate CometChat SDK			2.83	Pranay Prajapati
SCRUM Meeting and Team Discussion			0.33	Jayesh Rathod
Check and Update Sprint 5 Task Estimate			2.5	Jayesh Rathod
Working on Action Item & Update Task/Story			1.75	Jayesh Rathod
Jira – Confluence Page and Task Create			5.75	Jayesh Rathod
Jira – Confluence Page and Task Create			4	Jayesh Rathod
A
C			435.33
B
D
E
F

## 'file:///Users/auxano/Documents/untitled%20folder/SwiftUI/SwiftUI-Demo/Sheet%20Calc/GetUniqueValues.xls'#Logs
Item			Hours	Person
Test tournament leaderboard with different browser and devices			4	Dhruvin Soni
Test Push notification after upgrade push notification system			2.5	Dhruvin Soni
Test replace home screen image in application			1	Dhruvin Soni
Client Call and Demo Sprint 3			0.67	HasanAli
Client Call and Demo Sprint 3			0.67	Pranay Prajapati
TD - 128 -- IOS - Replace Home Screen image			1.5	Pranay Prajapati
TD - 128 -- IOS - Replace Home Screen image			0.17	Dhruvin Soni
TD - 136 -- AND - Player Card Loading Issue for Non-Tournament Users on Android			2.5	HasanAli
TD - 136 -- AND - Player Card Loading Issue for Non-Tournament Users on Android			0.5	Dhruvin Soni
TD - 133 -- WEB - Stage Statistics Leaderboard			0.17	Dhruvin Soni
Client Call and Demo Sprint 3			0.33	Dhruvin Soni
Client Call and Demo Sprint 3			0.33	HasanAli
Client Call and Demo Sprint 3			0.33	Pranay Prajapati
TD - 128 -- IOS - Replace Home Screen image			0.17	Dhruvin Soni
TD - 128 -- IOS - Replace Home Screen image			0.42	Pranay Prajapati
TD - 129 -- AND - Replace Home Screen image			0.17	Dhruvin Soni
TD - 129 -- AND - Replace Home Screen image			0.42	HasanAli
Client Call			0.4	Jayesh Rathod
TD - 132 -- BE - Stage Statistics Leaderboard			3	Kishan Dharajiya
TD - 134 -- BE - Manual Cron Run for DST Timezone Issue			0.25	Dhruvin Soni
TD - 126 -- BE - Upgrade Push Notification System to Latest APIs			0.17	Dhruvin Soni
TD - 125 -- AND - Upgrade Push Notification System to Latest APIs			0.25	Dhruvin Soni
TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs			0.25	Dhruvin Soni
TD - 126 -- BE - Upgrade Push Notification System to Latest APIs			0.25	Dhruvin Soni
TD - 132 -- BE - Stage Statistics Leaderboard			0.25	Dhruvin Soni
TD - 133 -- WEB - Stage Statistics Leaderboard			1	Dhruvin Soni
TD - 126 -- BE - Upgrade Push Notification System to Latest APIs			3.25	Kishan Dharajiya
TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs			0.5	Dhruvin Soni
TD - 125 -- AND - Upgrade Push Notification System to Latest APIs			0.5	Dhruvin Soni
Preparing Sprint & Client Discussion			1.5	Jayesh Rathod
Testing stage statistics leaderboard			5	Pranay Prajapati
TD - 125 -- AND - Upgrade Push Notification System to Latest APIs			4	HasanAli
TD - 133 -- WEB - Stage Statistics Leaderboard			4	Usama Shaikh
TD - 126 -- BE - Upgrade Push Notification System to Latest APIs			2.5	Kishan Dharajiya
TD - 132 -- BE - Stage Statistics Leaderboard			6.5	Kishan Dharajiya
TD - 124 -- IOS - Upgrade Push Notification System to Latest APIs			5.33	Pranay Prajapati
TD - 125 -- AND - Upgrade Push Notification System to Latest APIs			4	HasanAli
TD - 133 -- WEB - Stage Statistics Leaderboard			3	Usama Shaikh
TD - 134 -- BE - Manual Cron Run for DST Timezone Issue			0.5	Kishan Dharajiya
SCRUM Meeting and Team Discussion			0.5	Jayesh Rathod